## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | July 2013-June 2014
| Project Title: | Enhancing Adaptive Capacity of Communities to Climate Change-related Floods in the North Coast and Islands Region of PNG
| Project Summary: | The impact of climate change-related hazards in the Papua New Guinea (PNG) country has been increasing in intensity and frequency. Further impacts from climate change include the loss of food gardens due to extensive flooding (both in coastal and riverine areas) combined with extended periods of drought. The rising sea level is causing some of PNG’s islands to be gradually submerged. Salt water intrusion is affecting groundwater particularly in the islands and in coastal areas, threatening domestic water supplies and agriculture. With the onset and multitude of climate change impacts, the country’s economy, environment and people are becoming more vulnerable and are at risk of not meeting basic human development needs. Climate change puts at risk the achievement of the goals set out in PNG’s major development plans. Flooding in the coastal areas is one of the most important climate change related hazards in the North Coast and the Islands Region as settlements are usually located in the coasts, particularly the provincial capitals of East Sepik (Wewak), Madang (Madang), Morobe (Lae). Similarly, in the hinterland areas, climate change-related inland flooding is the most pressing hazard with the largest potential for wide-spread damage. The overall objective of this programme is to enhance the adaptive capacity of communities to make informed decisions about and adapt to climate change-driven hazards affecting both coastal and riverine communities in the North Coast and Islands Region of Papua New Guinea. In particular, the programme will focus on enhancing resilience towards occurrences of coastal and inland flooding events. The proposed programme will contribute to several outcomes and outputs listed within the Adaptation Fund Strategic Results Framework.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | PIMS 4452 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Papua New Guinea | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | East Sepik, Madang, Morobe, New Ireland and Northern Provinces in Papua New Guinea | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2012-03-23
IE-AFB Agreement Signature Date: |  | 2012-03-26 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2012-07-26 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | September 2015. Mid-term review was planned for October 2014 in the Project Document however, since the project has started 2 years late in implementation, it is now proposed for September 2015.
| Terminal Evaluation Date: | Last quarter of 2017
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | National Inception Workshop Report, New Ireland Provincial Stakeholder Consultative Meeting, Mangrove handbook, Hazard assessment project report and maps for the 5 provinces, Provincial inception workshop reports (New Ireland, Northern, Madang, Morobe, East Sepik), Early warning systems field assessment reports, presentations on the project. | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Maureen Ewai, Project Manager | Dominican Republic
| Email: | maureen.ewai@undp.org | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: | Varigini Badira | Equatoral Guinea
| Email: | vbadira@gmail.com | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Roy Trivedy | Fiji
| Email: | roy.trivedy@one.un.org | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Jacob Ekinye | Georgia
| Email: | jacobekinye@gmail.com | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | Emmajil Ahai-Bogari | Grenada
| Email: | emmajil.rowanna@gmail.com | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Luanne Losi-Yawingu | Guyana
| Email: | lulan2431@gmail.com | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: Cumulative from project start to 30 June 2013
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 30 June 2014 | 672130
Add any comments on AF Grant Funds. (word limit=200) | The key barrier to successful project implementation in the previous PPR period was the lack of sufficient human resources to implement the project. This issue was solved during this reporting period. The Project Management Unit including Project Assistant and Project Manager were brought on board in September and October 2013, respectively. In addition, an internal arrangement was made within UNDP CO for a Climate Change Specialist to join the Project Management Unit in May 2014. A Communications Specialist was hired in July 2014 for 6 months to produce awareness materials and raise the profile of the project. With support from the OCCD, UNDP and partner agencies including the National Weather Service and the Department of Environment and Conservation, the PMU has begun implementation of the Project at an accelerated speed. The key activities implemented to-date include completion of provincial inception workshops to introduce the project to the provinces, training of 3 National Weather Service staff on EWS in Australia (November 2013), training of three project coordinators from East Sepik, Morobe and New Ireland in August 2013, facilitate electronic media advocacy on climate change adaptation in support of national climate change day in August 2013, development of Provincial workplans, setting up of the Provincial Climate Change Committees in all pilot provinces followed by signing of MOAs with OCCD by two provinces (Morobe and Northern), initial site assessments for the Early Warning Systems Project, Hazard assessment for the 5 provinces which produced hazard maps and a draft report available. There are additional two large procurements in progress for the Early Warning systems and Vulnerability Needs Assessment which will begin August 2014 into early 2015. Partnerships are being established through Grant Agreements with the Non-Government Organizations, which will further accelerate the delivery of project activities in the provinces including two signed agreements for Madang Province.
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY /ACTION | AMOUNT
| ACTIVITY 1: Adaptation to Coastal Flooding-related Risks and Hazards for North Coast and Islands Region Communities | 278505.99
| 1.1 Coastal early warning systems established for observation, data collection and information management and dissemination in the North Coast and Islands Region | 82000
| 1.2 Coastal early warning systems established for observation, data collection and information management and dissemination in the North Coast and Islands Region | 60254
| 1.3. Support system for community-led mangrove reforestation and conservation projects | 80834
| 1.4 Integrated coastal adaptation measures implemented to protect 8 communities in East Sepik Province, Oro Province and New Ireland Province. | 55417.99
| ACTIVITY 2: Adaptation to Inland Flooding-related Risks and Hazards for Riverine Communities in East Sepik, Northern, Madang and Morobe Provinces | 128941.52
| 2.1 Inland flooding early warning systems established for observation, data collection and information management and dissemination in the provinces of the North Coast and Islands Region | 42376.61
| 2.2 Inland flood preparedness and response plan and systems established in the North Coast provinces | 45829.53
| 2.3 Integrated riverbank protection measures implemented to protect 8 communities in East Sepik Province, Oro Province and Morobe and Madang Provinces | 40735.3
| ACTIVITY 3: Institutional Strengthening to Support Climate and Disaster Resilient Policy Frameworks | 72093.19
| 3.1 Climate change-related risks and resilience from coastal and inland flooding integrated into coastal zone management related polices, legal and planning frameworks at the national and sub-national levels | 38837.28
| 3.2 Policy makers and planners at the national, provincial and district offices, institutions and extension services systemically trained to implement climate-sensitive policies and plans | 33255.91
| ACTIVITY 4: Awareness Raising and Knowledge Management | 46768
| 4.1 Lessons learned and best practices generated, captured and distributed to other communities, civil society, policy makers in government and globally through appropriate mechanisms | 17699
| 4.2 Climate change awareness and education programmes carried out to build next generations' resilience to climate change | 29068.61
| Activity 5: Project Management and Coordination | 57446.79
| TOTAL | 583756
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| ACTIVITY 1: Adaptation to Coastal Flooding-related Risks and Hazards for North Coast and Islands Region Communities | 960000 | 2015-07-01
| 1.1 Coastal early warning systems established for observation, data collection and information management and dissemination in the North Coast and Islands Region | 260000
| 1.1 Coastal early warning systems established for observation, data collection and information management and dissemination in the North Coast and Islands Region | 300000
| 1.3. Support system for community-led mangrove reforestation and conservation projects | 200000
| 1.4 Integrated coastal adaptation measures implemented to protect 8 communities in East Sepik Province, Oro Province and New Ireland Province. | 200000
| ACTIVITY 2: Adaptation to Inland Flooding-related Risks and Hazards for Riverine Communities in East Sepik, Northern, Madang and Morobe Provinces | 820000 | 2015-07-01
| 2.1 Inland flooding early warning systems established for observation, data collection and information management and dissemination in the provinces of the North Coast and Islands Region | 220000
| 2.2 Inland flood preparedness and response plan and systems established in the North Coast provinces | 200000
| 2.3 Integrated riverbank protection measures implemented to protect 8 communities in East Sepik Province, Oro Province and Morobe and Madang Provinces | 400000
| ACTIVITY 3: Institutional Strengthening to Support Climate and Disaster Resilient Policy Frameworks | 335000 | 2015-07-01
| 3.1 Climate change-related risks and resilience from coastal and inland flooding integrated into coastal zone management related polices, legal and planning frameworks at the national and sub-national levels | 135000
| 3.2 Policy makers and planners at the national, provincial and district offices, institutions and extension services systemically trained to implement climate-sensitive policies and plans | 200000
| ACTIVITY 4: Awareness Raising and Knowledge Management | 160000 | 2015-07-01
| 4.1 Lessons learned and best practices generated, captured and distributed to other communities, civil society, policy makers in government and globally through appropriate mechanisms | 60000
| 4.2 Climate change awareness and education programmes carried out to build next generations' resilience to climate change | 100000
| Activity 5: Project Management and Coordination | 200000 | 2015-07-01
| TOTAL | 2475000
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Procurement
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  | 6
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signiture Date | Payment to Date | Remaining Balance
Service Contract |  |  |  | -6999.67 | 6999.67
Service Contract |  |  |  | -1500 | 1500
Individual Contractor |  |  |  | 0 | 5000
Non-Micro Grant Agreement |  |  |  | 45000 | -45000
Non-Micro Grant Agreement |  |  |  | 22500 | -22500
Hazard Assessment |  |  |  | 41043 | 95737
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
Hazard Assessment for target provinces of East Sepik, Madang, Morobe, Northern and New Ireland International Contract (Institutional) 16th August 2014 |  |  | 136780 | Minimal financial proposal with qualification and experiences of the proponent
Assessment of Early Warning Systems (EWS) for inland and coastal flooding- East Sepik, Madang, Morobe, Northern and New Ireland Provinces, Papua New Guinea; International Contract (Institutional); August 14 |  |  | In progress
Climate Risk and Vulnerability Needs Assessment for Morobe, East Sepik, Madang, Northern and New Ireland Provinces of Papua New Guinea; International Contract (Institutional); August 14 |  |  | In progress
Capacity Needs Assessment for the 5 target provinces and the national agencies International Contract (Institutional); August 14 |  |  | In progress
PNG-wide climate risk and Vulnerability Needs Assessment (DFAT Funded); International Contract (Institutional); Sept 14
In progress
Hazard Assessment for additional provinces of West Sepik, Milne Bay, Central/NCD, Gulf and Western (DFAT funded); International Contract (Institutional); Sept 14 |  |  | In progress

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Insufficient collaboration between project implementation partners and stakeholders | M | Representation at the Project Steering Committee is inclusive of all relevant implementation partners and stakeholders. Regular updates of the project at the monthly climate change technical working group meetings have been conducted. Provincial Climate Change Committees (PCCC) have been established with chair being the Provincial Administrator or the Governor to keep stakeholders informed of activities in the provinces. PCCC is representative of different agencies in the province.
Weak cooperation by communities at proposed sites | M | Provincial Stakeholder workshops were conducted at the provincial centres and some of the initial site visits have been conducted in the sites identified in the project document especially for early warning systems and mangrove projects. Provincial inception in partnership with SGP CBA Outreach has generated interested from communities including those outside of the proposed sites.
Land use disputes within the communities affect implementation of project activities and plans | L | Provincial Stakeholder workshops were conducted at the provincial centres and some of the initial site visits have been conducted in the sites identified in the project document especially for early warning systems and mangrove projects. Through these consultations, strong support and cooperation is being established, with no concerns of land use disputes raised.
Limited human resources in PNG’s national and provincial agencies to adequately support to the activities and ensure the sustainability of the adaptation measures | M | The project has been able to support PNG’s national and provincial agencies through attracting national and international expertise to deliver high quality activities and outputs. For example, international expertise was brought in to conduct the Hazard Assessment in East Sepik, Madang, Morobe, Northern, and New Ireland provinces. Further expertise will be sourced nationally and internationally to continue to support the PNG government in implementing the Early Warning System Design, Vulnerability and Needs Assessment. With the view of building long-term capacity required for sustained project investments and benefits, the procurement for Climate Change Capacity Assessment consultancy has been initiated to start in August to assess and address training needs at the national, provincial, district and local level governments including private sector and civil society organisations. All major projects will include training components for sustainability of the projects. This was initiated with the Hazard assessment project.
A series of unusually adverse climatic conditions impacts the adaptation measures being implemented, or weakens the interest of key stakeholders to address adaptation issues. | L | The adverse climate change or disaster related impacts encourage communities to have keen interest and initiate adaptation measures. For example, a village community of Danu, West Coast Namatanai, New Ireland have been experiencing coastal erosion on the former mangrove sites that the community have cleared in the past. This experience has led them to start a mangrove nursery to replant mangroves. In Northern Province, the communities have taken advantage of the silt built from flood events in cylone Guba in late 2007/early 2008 to revegetate the area near Baoroda island.
The best practices and adaptation measures adopted are not gender sensitive – i.e. they increase inequity between men and women or change the social roles of men and women in a way that reduces self reliance. | M | Hazard maps provide information that will be useful for planning, eg. It provides information on the number/amount of households and population, villages/settlements, local level governments that are likely to be affected by future flooding. The project is initiating some of the activities in the provinces with the use of these maps, eg. Madang province, through the Grant Agreement with Foundation for People and Community Development as one of the outputs to develop community based disaster risk management planning along the upper and middle Ramu River. Through this activity, roles of men, women and children will be identified and trained in the adaptation measures that communities identify through the process.
The selection of pilot sites does not follow the established criteria and is derailed due to political processes and influences. | L | This risk has been avoided as pilot sites were selected based on criteria established by the Project Document as well as through site visits, community consultations, and considerations for security. Some of the sites identified in the project document were verified during the provincial inception workshops and initial site visits to some areas especially for the early warning systems and mangrove projects. One of the mangrove sites Turubu in East Sepik was visited and realised there were no mangroves. During the Provincial inception workshop, Murik Lakes was recommended to be included instead of Turubu. In New Ireland, Djaul Island will no longer be a mangrove project site due to murder of an environmental advocate from the area. The murder has been reported due to issues related to land dispute and not related to the project. However, in order to ensure the safety of people involved in the project, the mangrove planting initiatives will be now implemented in New Hanover (identified site in prodoc) and main island (in Namatanai District instead of Djaul Island). Safety levels of these new locations are expected to be significantly better because of absence of disputes among communities. Besides, the communities are highly interested in mangrove conservation/protection. The provincial authorities also assessed the security situation in these communities as normal. Throughout the project, safety of the people involved is priorities, with tangible measures instituted such as prior assessment of security situation before any field/site visits, consultation with local authorities and leaders to assess the local dynamics and security situation, providing information to communities in advance regarding proposed site visit etc. The project is yet to experience political influences
The government is not supportive, politically and financially, to a cross-sectoral and integrated approach to the management of climate risks and opportunities. | L | All provincial Climate change committees have been established in the 5 target provinces. Support at have been formalized through Memorandum of Understanding signed between OCCD and Northern and Morobe Provincial Administrations.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The project is facing stiff competition from the fluorishing resource extractive industry in attracting the best candidates for the full-time project positions (National Program Coordinator - NPC, Admin and Finance Specialist and Technical Specialist). Qualified professionals are in short supply relative to demand from all sectors. | M | The Project Manager and Project Assistant-Finance and Administration, Communications Specialist have been hired. Internal UNDP CO arrangement allowed for the Technical Specialist to be endorsed to support the project. Additional support from OCCD staff and NWS/DEC staff are assisting the project to deliver some of the initial activities and large procurements are beginning. Grant Agreements signed initially with WWF and FPCD, and additional agreements will ensure delivery of outputs/outcomes of the project.
Procurement policies/guidelines under UNDP NIM/DIM Implementation Modality is likely to hinder implementation on the ground | H | Non Micro Grant Agreements are developed with provincial specific partner agencies to improve delivery of project activities.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
"Weak cooperation by communities at proposed sites (risk). One of the central principles of the replication support is to support activities that are initiated by communities and have appropriate management/support structures in place (mitigation measure)." This is in relation to the mangrove projects in both Madang and New Ireland Provinces. In Madang, through partnership with World Wide Fund for Nature (grant agreement), their experiences in mangrove nursery and planting with Bilia and Pana communities in Madang Lagoon will be replicated to the mouth of Ramu River which is the target site for the project in Madang. In New Ireland, representatives from Danu in West Coast Namatanai have been trained in mangrove nursery and planting, and proposal writing through the GEF Small Grants Programme. The Danu community has a mangrove nursery in the village with support from the New Ireland Provincial Administration. This is also a potential site for the early warning systems project. This effort will be replicated to the other communities including those in the identified sites.
Note on E16: Shoko Takemoto: to be completed and updated with Rabi's inputs

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Recruitment of Project Staff (PMU) |  | Recruitment of Project Associate to be finalised and additional staff and consultants to be hired to assist specific projects such as early warning systems, VNA, capacity assessment and mangrove trainer. Also recruit the 5 Provincial Project Assistants to be based in the provinces |  | Project Assistant-Finance and Administration, Communications Specialist and Technical Specialist on board | Satisfactory
| Initiated major projects including Grant Agreements for implemntatio of community level adaptation measures. |  | Procurement process have begun for Early Warning Systems project, Vulnerability Needs Assessment, Capacity Assessment, Nationwide VNA is funded by DFAT, additional hazard assessment for 5 provinces (West Sepik, Milne Bay, Central/NCD, Gulf and Western is funded by DFAT. These projects will start in 3rd quarter of 2014. Capacity Assessment for Climate Change Adaptation has also been initiated |  | Terms of references completed, assessment of the Terms of reference done. Began the process to engage a Procurement expert to assist the project to hire the consultants for the EWS and VNA. Hazard assessment completed for the 5 target provinces completed. TOR for capacity assessment approve by OCCD and other stakeholders and recruitment process to hir consultants started. Two GAs have beens igned with NGOs to undertake Community based CCA activities | Marginally Satisfactory
| Memorandum of Understanding between OCCD and the 5 target provincial administrations |  | MoUs with the New Ireland, Madang and East Sepik Provinces need to be signed after the PCCC has been endorsed by the Provincial Executive Council. |  | MoUs for Morobe and Northern Provinces have been signed. | Marginally Satisfactory
[5 empty] | Overall Rating | Marginally Satisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Maureen Ewai
| Email: | maureen.ewai@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
With the Project Manager, Project Assistant and Technical Specialist on-board, progress has been made with provincial inception workshops completed and 2014 provincial workplans developed. Initial assessments for the EWS and some mangrove sites have been completed. The project has built a workstation. Hazard assessment project has been completed and a draft report is available with satisfactory results from the hazard maps for the provinces for both inland and coastal flooding. This maps are useful for provincial and local level government development planning, decisions and budget allocations. The current efforts ensure the results are presented to the decision-makers. The mangrove handbook has been completed and the first 50 copies will be used to trial training in Madang from 24-25 July. Procurements for the EWS, VNA and Capacity Assessments have begun for the target provinces. Additional nation-wide VNA study and Hazard assessment for the additional 5 provinces will be conducted with the Australian Government funding. The procurement for the DFAT projects have been begun. The job of Provincial project Assistants for the 5 provinces will be advertised through OCCD, in July and should be recruited in August 2014.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Some of the key activities under each component implemented |  | continue with planning, procurement and implementation of other activities such as Vulnerability Needs Assessment |  | Completed hazard mapping, inception workshops, built workstation for the PMU, mangrove handbook printed | Satisfactory
| Building relationship with key agencies in the provinces to improve delivery of project activities |  | Develop additional 3 grant agreements for Madang, for East Sepik, Morobe, Northern and New Ireland Provinces |  | Signed grant agreements with World Wildlife Fund for Nature and Foundation for People and Community Development for Madang province | Satisfactory
| Provincial Climate Change Committees |  | Provincial Executive Council to formally endorse the PCCCs |  | PCCC have been established in all 5 target provinces | Marginally satisfactory
[5 empty] | Overall Rating | Satisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Jacob Ekinye
| Email: | jacobekinye@gmail.com
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other | Database of coastal and inland flooding hazards established |  | Identification of data and host insitutions for the database to be established |  | Hazards Data identified during the Hazard Assessment and identification of host institution is pending completion of Analysis of EWS in PNG | Marginally satisfactory
| Disaster preparedness plans fully established |  | Establishment of Provincial disaster management plans was pending completion of Hazard Assessment |  | Almost all provinces initiated dialogue to review and finalise provincial disaster management plans after completion of Hazard Assessments of all pilot provinces. The Climate Risk Assessment will also feed into development of integrated Plans combining DRM/CCA | Marginally satisfactory
| Policy briefs and dialogue sessions for high-level policy makers |  | At least one annual high level forum on climate change adaptation |  | Project has facilitated provision of strategic policy guidance as and when necessary during the reporting period. Preparations are underway with Department of Environment and Conservataion for a High Level Forum in September 2014 | Satisfactory
[5 empty] | Overall Rating | Marginally satisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Gwen Maru
| Email: | gwen.maru@undp.org
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | Database (risk information systems) for data and information on climate risks for PNG has been identified as significant for development planning. While hazard assessment project was conducted, it was difficult to engage with institutions and agencies responsive to sharing data for the study. The outcome of the hazard assessment project has been very rewarding with the hazard maps which will be widely shared to planners, decision makers and development partners. The data from the hazard assessment and other projects will be managed by a responsible agency yet to be identified. The capacity needs assessment project will assist in identifying a national agency with capacity to build and manage the database. The Hazard assessment and VNA results will be used assist in the disaster preparedness plans for the provinces. Provinces such as Madang has identified communities along the Ramu River to develop disaster risk management plans that will link up to the provincial plans.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective - Strengthened ability of coastal and riverine communities in Papua New Guinea to make informed decisions about and to undertake concrete actions to adapt to climate change-driven hazards affecting their specific locations | 1. Number of risk-exposed coastal communities protected through adaptation measures | In the current scenario, risk-exposed communities are to a large extent unable to adapt to climate change due to a lack of resources, capacity, knowledge and the necessary support through provincial and national institutions as well as policy frameworks. With the scale of adaptation measures planned for implementation the total population in the 16 targeted communities would be an estimated 32,000 | 5 provincial inception workshops completed. Workplans have been developed and starting to visit some communities. | By the end of the project at least 8 coastal communities are protected through adaptation measures against coastal flooding scenarios, with attention to the special concerns of women as participants and beneficiaries.
| 2. Number of risk-exposed riverine communities protected through adaptation measures |  | 5 provincial inception workshops completed. Workplans have been developed and starting to visit some communities. | Eight (8) riverine communities are protected through adaptation measures against inland flooding, with attention to the special concerns of women as participants and beneficiaries
| 3. Number of provinces with improved climate-related planning and policy frameworks to increase resilience |  | Capacity assessment project procurement process has began. The project will start in September 2014 into 2015 | At the end of the programme, adaptation to climate change is managed, monitored and planned at the provincial level in the targeted provinces and supported by a framework of policies and plans including disaster preparedeness and response plans, coastal zone management plans.
Outcome 1 - Reduced exposure and increased adaptive capacity of coastal communities to flood-related risks and hazards in 8 communities and three cities of the 11 provinces of the North Coast and Islands Region. | 1. Number of communities benefitting from improved protection from coastal floods | The vast majority of communities exposed to coastal flooding is inadequately equipped with resources, capacity and support to adapt to the heightened risks from climate change The total number of inhabitants in the 8 target coastal communities that are vulnerable to coastal flooding is estimated at 16,000. An additional population of 120,000 in the cities of Lae, Wewak and Madang will benefit from the programme’s implementation | 5 provincial inception workshops completed. Workplans have been developed and starting to visit some communities. | By the end of the project, 8 communities are protected from coastal flooding through adaptation measures that were put in place in a community-led way with the agreements/compacts agreed on by communities to preserve the mangrove forests
| 2. Number of AWS and voluntary weather stations in operation 3. Number of communities covered by the improved coastal warning system and weather information | There is lack of equipment and capacity of the PNGNWS, hence, the forecasting of disasters and extreme weather events is severely limited. | Initial site visits were conducted in all provinces for the EWS project | At least 6 tidal gauges and at least 6 AWS and 10 voluntary weather stations established at strategic locations, meet WMO standards and contribute to the monitoring and early warning system. One AWS will have been installed in each target 8 communities.
| 4. Number of provinces wth comprehensive disaster prepared ness and response plans for coastal flooding in place | The provincial and national-level disaster management frameworks are evidently inadequate to address the risks | Provincial inception workshops have been completed and provinces have developed their workplans. | At least four provinces will have a comprehensive disaster preparedness and response plans for coastal flooding in place and will have conducted dry run tests.
| 5. Number of provincial capitals with assessed engineering measures for adaptation | No effort has been done on this aspect in the target provincial capitals. | This activity will be implemented in 2015 | For three provincial capitals of Lae, Madang and Wewak suitable coastal engineering measures for adaptation are identified and addressed through respective planning and funding.
| Number of community-led mangrove projects benefitting from support system for mangrove projects | Community-based mangrove projects are undertaken ad-hoc and largely without sufficient expertise and support | Mangrove training on nursery and planting has began in Madang. Trainers are required to conduct training in their communities with the use of mangrove handbook | 33 community-led mangrove conservation and/or reforestation projects, covering about 100 hectares are supported through the support network and nurseries
| Number of mangrove nurseries established and sustainably operating | None | Mangrove training on nursery and planting has began in Madang. Trainers are required to conduct training in their communities with the use of mangrove handbook | Eight (8) regional nurseries operate sustainably supplying the requirements of the target sites and replication areas
| Resources allocated for continued operations of the nurseries |  | Mangrove training on nursery and planting has began in Madang. Trainers are required to conduct training in their communities with the use of mangrove handbook | Before the end of the project, sufficient resources are allocated by government for the continued operations of the nurseries beyond the life of the project.
Outcome 2 - Reduced exposure and increased adaptive capacity of 8 riverine communities in 4 provinces | Number of communities benefitting from improved protection from inland flooding | The vast majority of communities exposed to inland flooding risk is inadequately equipped with resources, capacity and support to adapt to the changed scenario The total number of inhabitants in the 8 target riverine communities that are vulnerable to coastal flooding is estimated at a minimum 32000 people. | Inception workshops have been completed. Some provinces such as Madang have identified the LLGs and Wards to conduct community based disaster risk management plans and adaptation measures | By the end of the project, eight communities are protected from inland flooding through adaptation measures that were put in place in a community-led way.
| Number of communities covered by the improved warning system and weather information Number of AWS and voluntary weather stations in operation | Disaster preparedness is limited by the lack of and state of facilites and plans There is lack of equipment and capacity of the PNGNWS is weak, hence theh forecasting of disasters and weather patterns is limited. | Procurement for the EWS project began. EWS awareness especially for Madang will begin in August 2014. | At least 6 AWS and at least 20 voluntary weather stations established at strategic locations, meet WMO standards and contribute to the monitoring and early warning system. One AWS will have been installed in each target 8 communities.
| Number of provinces with comprehensive disaster preparedness and response plan for inland flooding | The provincial and national-level disaster managment frameworks are evidently inadquate | Inception workshops have been completed. Provincial workplans have been developed including plans for disaster preparedness plans. | At least four provinces will have a comprehensive disaster preparedness and response plan for inland flooding in place and will have conducted dry run tests.
Outcome 3 - Strengthened institutional capacity at national and sub-national levels to integrate climate change-related risks into sectoral policies and management practices | Number of national and provincial level policies, strategies, plans and coordinating mechanisms reviewed and incorporating resilience to climate change | Adaptation to the changed climate scenario of the present and future is inadequately considered in national and provincial level policies and planning frameworks | Provincial climate change committees have been established for the 5 target provinces | At the end of the project, all major development plans in the targeted provinces reflect climate change and adaptation considerations and coastal zone management policies are developed for the most populated areas (especially Wewak, Kavieng, Madang, Lae)
| Number of provincial and national-level officers trained in climate adaptation planning and implementation | At the provincial level the lack of resources, capacity and in some cases basic management mechanisms/plans is evident | 3 NWS staff, 3 provincial Coordinators, 23 participants from the 5 target provinces were trained in mangrove nursery and planting | At the provincial level, there is a strong link between all climate change officers/focal points and the communities in their respective provinces and the officers are equipped with the resources and capacity to identify and manage adaptation needs in the province
| Participation of women in project activities | Participation of women is very minimal | 5 women were trained in mangrove nursery and planting | Increased (at least 20%) number of women participating in capacity building activities at national and subnational level
Outcome 4 - Strengthened awareness and ownership of adaptation and climate change-related risk reduction processes at national and sub-national levels | % of the risk-affected population exposed to awareness raising activities and materials | Awareness raising efforts is ad-hoc, uncoordinated and often undertaken with insufficient technical basis | The project has initiated radio, newspaper and television news to raise awareness. A Communications Specialist is on board and is working on awareness materials/ideas, strategy | 75 % of the risk-affected population is exposed to awareness raising activities and materials.
| Integration of climate change into the national school curricula and university academic programmes | Only few schools cover climate change in their classes and activites; there is very limited guidance for teachers | From discussions with the Education Department, climate change is not a core subject for primary or secondary schools. It has been suggested to develop guide materials. For effective delivery, the project will instead work with selected schools in the provinces to develop climate change related activities. | The topics of climate change and adaptation are introduced in PNG’s school curricula and university academic programmes and teachers are equipped with the required knowledge and material
| Amount of funding mobilized via CSR and sponsorship agreements | CSR funding sources is currently nil. | No progress on this | By the end of the project agreements on continuation of awareness raising and adaptation activities (especially replication) through contributions from Corporate Social Responsibilty programmes and private sector participation are reached (including projects under infrastructure tax credit schemes) and make resources available for the community-led adaption in at least 10 further communities (estimated 500,000 USD)

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Lengthy procurement processes delayed the implementation of project activities.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | PMU is on board, but additional project staff and consultants are required to improve the delivery of project activities. Procurement process is in place to hire consulting companies to assist with major project implementation.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | Mangrove project sites have changed in East Sepik (from Turubu to Murik Lakes as agreed during the provincial inception workshop). This is due to non-availability of mangroves at Turubu. Change from Djaul island to Namatanai in New Ireland for the mangrove project due to security reason.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Equal number of men and women should be included in activities such as trainings. In mangrove training, there were 5 women of the 23 participants. Approaches to increase participation of women, such as hosting separate activities targeting women,this needs to be considered in the next project activities.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Linking closely with National Policies and Priorities and using the project as one of the many vehicles to deliver these objectives have been effective. This has allowed the project to successfully create new institutions and policy frameworks that would enhance climate resilience, such as the establishment of the Provincial Climate Change Committees and Disaster Management Plans at the provincial levels.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The know-how and processes developed to establish institutions to enhance community climate resilience mentioned above will be replicated throughout the nation, outside the project area.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Establishment of formal partnerships through MoUs and Grant Agreements are effective in building on existing expertise and efforts of implementing concrete adaptation interventions on the ground, as seen through the initial work that has started in establishing mangrove nursery and planting, hazard mapping, vulnerability and capacity assessments.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The work on mangrove nursery and planting, hazard mapping, vulnerability, and capacity assessments that are tested and developed at the selected sites can also be replicated to other regions and sites in the country.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Willingness, innovative/initiative, eager to learn and take on board to be practical
What measures are/have been put in place to ensure sustainability of the project/program results? | Developing relationship with the provincial administrations including MoU for sustainability of projects
What measures are being/could have been put in place to improve project/program results? | Obtaining gender equity in project participation is a challenge. The project will explore measures to reach out to more women in the coming year, by understanding the different roles and challenges faced by men and women, and if necessary due to social and safety concerns, organizing separate outreach activities targeted for men and women.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | The hazard maps developed from the hazard assessment project will be used to identify communities that are likely to be affected by the floods to implement adaptation measures for coastal and river communities. Furthermore, mangrove handbooks were developed so that community members can enhance their understanding and capacity on mangrove nursery and planting.
If learning objectives have been established, have they been met? Please describe. | Targeted training to build national capacities on EWS and communication were conducted in this reporting period. 3 National Weather Service staff were trained on EWS in Australia (November 2013). In addition three project coordinators from East Sepik, Morobe and New Ireland were trained in August 2013, facilitate electronic media advocacy on climate change adaptation in support of national climate change day in August 2013.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Lack of agency cooperation to provide important hazard data/information for the 5 provinces. Signing MoU between agencies may resolve this issue and allow for the data and information to be shared.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Training and capacity building to enhance technical expertise of national and local government staff is expected to contribute to the achievement of project outcomes. As an output of the EWS training, NWS was able to develop an initial specification and design of the EWS, which will be further refined through findings from various assessments including Hazard Mapping, Vulnerability and Capacity Assessments. Electronic media advocacy training has equipped provincial officers to communicate information, and mobilize support and participation that would enable project to have more wider and sustainable impacts.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Please select the relevant Fund level Outcome and Output indicators that align with the project objectives and outcomes
OBJECTIVE 1
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 1 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 1 | Adequate threat and hazard information on coastal and inland flooding disseminated in 8 coastal and 8 riverine communities reducing climate related risks to the affected population | A preliminary EWS has been set up recently with private public partnership established to disseminate information using mobile services. However, coastal and inland communities are still inadequately prepared to respond to flooding risks due to lack of knowledge, resources and capacity
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 5 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 5 | Critical coastal ecosystems restored to protect coastlines and provide livelihoods | Critical coastal ecosystems are degraded due to lack of recognition of the protective functions of coastal ecosystems
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 1 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individual or community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced+D16 | 1.2 | Early warning systems in 8 coastal and 8 inland communities installed | Forecasting and of disasters and extreme weather events is severely limited at the community levels due to lack of equipment and capacity of the PNGNWS
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 5 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individual or community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced+D16 | 5 | 33 community-led mangrove conservation and/or reforestation projects are supported | No community-led mangrove conservation and/or reforestation projects ongoing in targeted communities
OBJECTIVE 2
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 2 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 2.1 | At the end of the project, major development plans in the targeted provinces reflect climate change and adaptation considerations | At the national level, a Climate-Compatible Development Strategy (CCDS) and Interim Action Plan has been developed. However, there at the provincial level, there are no development plans or policies that adequately consider adaptation to the changed climate scenario
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 2.1 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individual or community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 2.1.2 | At the provincial level, there is a strong link between all CC officers/focal points and the communities and staff capacity to identify and manage adaptation needs increased | There is lack of resources and capacity to understand and respond to climate change, due to the lack of CC officers/focal points at the provincial level
OBJECTIVE 3
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 7 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 7 | Critical coastal ecosystems restored to protect coastlines and provide livelihoods | The protective functions of coastal ecosystems are not generally recognized
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 7 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individual or community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 7.1 | Climate change risks and resilience to flooding integrated into national and provincial planning frameworks | National economic and land-use planning frameworks have not yet sufficiently integrated climate change risks and flood resilience. The Environmental Impact Assessment process does not take climate change into consideration
OBJECTIVE 4
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 3 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 3.1 | Communities in the coastal and inland areas targeted by the intervention are aware of adaptation and climate risk reduction processes | Communities in the coastal and inland areas targeted by the intervention are not sufficiently aware of adaptation and climate risk reduction processes due to lack of effective knowledge products and education programmed
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 3 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individual or community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 3.1 | 50% of the community members in the coastal and inland areas targeted by the intervention are exposed to awareness raising activities and materials | Community members in the coastal and inland areas targeted by the intervention are not exposed to sufficient awareness raising activities or materials

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.

## Compatibility Report
Compatibility Report for Copy of PNG AF Project Progress Report_July12-July13.xls
Run on 9/18/2013 21:30
The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when opening this workbook in an earlier version of Excel or if you save this workbook in an earlier file format.
Significant loss of functionality | # of occurrences | Version
One or more cells in this workbook contain data validation rules which refer to values on other worksheets. These data validation rules will not be saved. | 3
| FinancialData'!E54 | Excel 97-2003
| Procurement'!E49:H49 | Excel 97-2003
| Risk Assesment'!E57 | Excel 97-2003
Minor loss of fidelity
Some formulas in this workbook are linked to other workbooks that are closed. When these formulas are recalculated in earlier versions of Excel without opening the linked workbooks, characters beyond the 255-character limit cannot be returned. | 2 Defined Names | Excel 97-2003
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 183 | Excel 97-2003