## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 26 May 2014 - 25 May 2015
| Project Title: | Developing climate resilience of farming communities in the drought prone parts of Uzbekistan
| Project Summary: | The project objective is to develop climate resilience of farming and pastoral communities in the drought prone parts of Uzbekistan, specifically Karakalpakstan. The project will help the central, regional and local governments and vulnerable farmers and pastoralists to withstand the current and future impacts of climate change: aridification and projected drying of this region that places serious strains on water availability resulting in a decline in land productivity. The project is comprised of four main components: (i) institutional capacity and mechanisms for drought risk management and early warning; (ii) climate resilient agricultural and pastoral production systems; (iii) landscape level approach to adaptation to climate change risks of increased aridity; (iv) knowledge management and awareness raising.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | PIMS 5002 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Uzbekistan | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Karakalpakstan, including Muynak, Kegeyli, Takhtakupir, Chimbay, and Kanlykol districts | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2014-02-10
IE-AFB Agreement Signature Date: |  | 2014-03-07 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2014-05-26 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2017-05-01
| Terminal Evaluation Date: | 2020-02-01
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Inception Report Press Releases in mass media Multi-Year Work Plan and Budget Schedule Mission Reports Quarterly Reports and Annual Report in Atlas Minutes of Project Board meetings Project one-pager Project Brief information at http://www.uz.undp.org/content/uzbekistan/en/home/operations/projects/environment_and_energy/developing-climate-resilience-of-farming-communities-in-the-drou.html Article about project in national mass media, see at http://www.uzdaily.com/articles-id-29699.htm and http://www.uzdaily.uz/articles-id-22264.htm | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://www.uz.undp.org/content/uzbekistan/en/home/operations/projects/environment | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Mr. Aleksandr Merkushkin | Dominican Republic
| Email: | aleksandr.merkushkin@undp.org | Ecuador
| Date: | 2014-09-14 | Egypt
| Government DA |  | El Salvador
| Name: | Prof. Viktor Chub, General Director of Uzhydromet | Equatoral Guinea
| Email: | uzhymet@meteo.uz | Eritrea
| Date: | 2011-04-12 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Mr. Yusuke Taishi; Ms. Rano Baykhanova | Fiji
| Email: | yusuke.taishi@undp.org; rano.baykhanova@undp.org | Finland
| Date: | 2014-05-01 | France
| Executing Agency |  | Gambia
| Name: | Prof. Viktor Chub, General Director of Uzhydromet | Georgia
| Email: | uzhymet@meteo.uz | Germany
| Date: | 2014-09-04 | Ghana
| Executing Agency |  | Greece
| Name: | Ms. Malika Nazarova, Deputy Head of Department on Pollutions Monitoring, Uzhydromet | Grenada
| Email: | uzhymet@meteo.uz | Guatemala
| Date: | 2014-09-15 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 25 May 2015
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 25 May 2015 | 164863
Add any comments on AF Grant Funds. (word limit=200) | So far, US$164,863 AF grants have been received in one initial tranche, of which US$56,784.32 have been disbursed and $108,078.68 are committed. The actual delivery of project AF funds, as of mid-March 2015, for the received tranche is 34.4% (and 1.15% of the total AF grant). However, the delivery of the first tranche of the AF fund is expected to be over 80% by the middle of April. Most importantly, the procurement process for automated observation networks and ICT equipment is expected to complete by April. This procurement accounts for nearly 70% of the outstanding commitments. Disbursement of AF grants during the current reporting period experienced delays due to the administrative and operational procedures required during the inception phase of the project including the mandatory governmental procedures applied to all international grant projects, recruitment of project management personnel and project office establishment.
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| 1.1 Upgraded observation and monitoring infrastructure (e.g. 2 Doppler water meters, automatization of 8 met stations) for effective data receiving and transmission | 26939.33
| 1.2. Multi-module platform for integration of data flow from hydro-meteorological observation network to end users | 0
| 1.3. Drought early warning mechanisms (indicators, gauges, warning distribution mechanisms etc.) to minimize impacts of droughts in place and functional | 3060.48
| 1.4. Science-based extension services for subsistence dekhan farmers established to assist in farm-based climate risk management, including sub-district, community level Climate Field School/Extension (CFS /E) for direct outreach to farmers and localized training in adaptation practices | 14878.19
| 2.1. 40,000 Dekhkan farmers have adopted climate resilient conservation agriculture practices (e.g. low till, mixed cropping, fodder production, and residue crop soil covering adopted measures adopted at 80,000 ha of dekhkan farms) | 0
| 2.2. 40,000 Dekhan farmers have adopted water saving irrigation practices (e.g. land leveling, well management, furrow and drip irrigation systems adopted at 80,000 ha dekhkan farms to improve farm-level drainage and minimize salinization) | 0
| 2.3. 40% of targeted dekhan farmers have established horticulture greenhouses on 20,000 ha of farms to minimize impacts of droughts on farm production | 0
| 2.4. Legal and regulatory framework put in place to support well tested farm-based adaptation measures for replication and upscale | 0
| 3.1. Local saksaul and tamarix plantations deliver sand stabilization and soil desalinization function for 1,042,094 ha of farm and adjacent farmlands, based on wind models and comprehensive landscape rehabilitation and management plan | 0
| 3.2. Community management scheme for planting and maintenance established as community employment scheme for landscape level adaptation | 0
| 3.3. Cooperative management for landscape rehabilitation and management established to enhance community control and ownership arrangements | 0
| 4.1. Inventory of all tested agronomic and water saving measures to map out successful practices | 0
| 4.2. Analysis and lessons learned for climate resilient agricultural and pastoral production systems in arid lands documented and disseminated through printed and web-based publications | 0
| 4.3. Quarterly farm and pasture land demonstration meetings with participation of national, local authorities, media and communities delivered | 623
| 5. Project management | 11283.32
| TOTAL | 56784.32
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 1.1. Upgraded observation and monitoring infrastructure (e.g. 2 Doppler water meters, automatization of 8 met stations) for effective data receiving and transmission | 536137.4 | 2016-05-01
| 1.2. Multi-module platform for integration of data flow from hydro-meteorological observation network to end users | 4000 | 2016-05-01
| 1.3. Drought early warning mechanisms (indicators, gauges, warning distribution mechanisms etc.) to minimize impacts of droughts in place and functional | 7870 | 2016-05-01
| 1.4. Science-based extension services for subsistence dekhan farmers established to assist in farm-based climate risk management, including sub-district, community level Climate Field School/Extension (CFS /E) for direct outreach to farmers and localized training in adaptation practices | 2135 | 2016-05-01
| 2.1. 40,000 Dekhkan farmers have adopted climate resilient conservation agriculture practices (e.g. low till, mixed cropping, fodder production, and residue crop soil covering adopted measures adopted at 80,000 ha of dekhkan farms) | 173179.01 | 2016-05-01
| 2.2. 40,000 Dekhan farmers have adopted water saving irrigation practices (e.g. land leveling, well management, furrow and drip irrigation systems adopted at 80,000 ha dekhkan farms to improve farm-level drainage and minimize salinization) | 21500 | 2016-05-01
| 2.3. 40% of targeted dekhan farmers have established horticulture greenhouses on 20,000 ha of farms to minimize impacts of droughts on farm production | 330000 | 2016-05-01
| 2.4. Legal and regulatory framework put in place to support well tested farm-based adaptation measures for replication and upscale | 4550 | 2016-05-01
| 3.1. Local saksaul and tamarix plantations deliver sand stabilization and soil desalinization function for 1,042,094 ha of farm and adjacent farmlands, based on wind models and comprehensive landscape rehabilitation and management plan | 7750 | 2016-05-01
| 3.2. Community management scheme for planting and maintenance established as community employment scheme for landscape level adaptation | 6200 | 2016-05-01
| 3.3. Cooperative management for landscape rehabilitation and management established to enhance community control and ownership arrangements | 0
| 4.1. Inventory of all tested agronomic and water saving measures to map out successful practices | 0
| 4.2. Analysis and lessons learned for climate resilient agricultural and pastoral production systems in arid lands documented and disseminated through printed and web-based publications | 0
| 4.3. Quarterly farm and pasture land demonstration meetings with participation of national, local authorities, media and communities delivered | 13635 | 2016-05-01
| Project management and implementation costs | 53564 | 2016-05-01
| TOTAL | 1160520.41
How much of the total co-financing as committed in the Project Document has actually been realized? | From the committed UNDP's cofinancing (USD200,000), $2,947.7 was used to cover the costs associated with direct project support services such as assistance to procurement and recruitment. Other expenditures were as follows: $2,2223.87 for international and national travels; $1,900 for Services $130.86 for Bank charges $0.04 for Realized loss Totalactually realized is USD7,354.24
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | N/A

## Procurement
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  | 10 contracts under USD 2,500 with total value of USD 7,347.63
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signature Date | Payment to Date | Remaining Balance
Service contract (Project manager) |  |  | 2014-09-16 | 14184 | -14184
Individual consultant (Photographer) |  |  | 2014-10-15 | 150 | -150
Purchase order (Printing services) |  |  | 2014-10-17 | 432 | -432
Purchase order (procurement of rollups) |  |  | 2014-10-20 | 293.75 | -293.75
Purchase order (Printing banners) |  |  | 2014-10-20 | 76.17 | -76.17
Institutional contract (Rent of translation equipment) |  |  | 2014-11-04 | 496.09 | -496.09
Purchase order (procurement of mobile phone) |  |  | 2014-11-25 | 299.62 | -299.62
Individual consultant (Translator) |  |  | 2014-11-25 | 589.4 | -589.4
Service contract (NFC) |  |  | 2015-03-01 | 0 | 0
Individual consultant (NC on automated hydrometeorological network supportive IT equipment) |  |  | 2015-03-10 | 0 | 0
Individual consultant (NC on water balance control facilities) |  |  | 2015-03-10 | 0 | 0
Individual consultant (NC on drought EWS) |  |  | 2015-03-10 | 0 | 0
Individual consultant (NC on reviewing thematic printing) |  |  | 2015-03-10 | 0 | 0
Service contract (AFA) |  |  | 2015-03-16 | 0 | 0
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
Procurement of Vehicle, Direct contracting, 28.01.2015 |  |  | 25000 | Lowest price among offers of locally available official distributors was selected.
Event management services (workshop), Micro purchasing, 08.10.2014 |  |  | 4865 | Lowest price offer among technically compatible quotations
Repair of building roof , Micro purchasing, 04.12.2014 |  |  | 2,855.93 | Lowest price among technically qualified offers
Procurement of furniture, Micro purchasing, 14.11.2014 |  |  |  | Lowest price among technically acceptable offers
4993.71

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
1. Reluctance of farmers or pastoralists to depart from over-irrigation and overutilization of inputs approach towards climate resilient conservation agriculture | Low | Two field trips were undertaken during the Inception Phase and farmers and representatives of rural communities vulnerable to climate change were met. During these meetings they had been introduced with advantages of innovative water saving and conservation agriculture technologies that can increase their resilience to droughts and other climate change impacts. Understanding of potential benefits reduces the risk of their reluctance to shifting from over-irrigating to water efficient and saving practices.
2. Repeated drought | High | The acquired practical experience on application of water saving technologies and early drought warning systems piloted in the most southern region of Uzbekistan - Kashkadarya province suffered from severe droughts - within UNDP project "Climate Risk Management in Uzbekistan" as well as experience gained within a number of relevant international and national projects and programs dealt with drought risk reduction were explored and considered to adjust best practices to the needs of Adaptation Project and implement further in Karakalpakstan's environment. Risk is not reduced yet during the reporting period but will be reduced during next reporting period as soon those adjusted best practices start to be implemented in pilots in Karakalpakstan.
3. Low level of cooperation between executing institutions | Low | The high level meeting (sub-national) was conducted within the project inception phase to establish partnership for coordination of project activities among all stakeholders under supervision of the Chairman of the Council of Ministers of Republic of Karakalpakstan. Moreover, two Inter-Agency Working Groups (at national and sub-national levels) aimed at strengthening coordination and cooperation of all stakeholders involved in Adaptation Project were established by the government resolutions. Their composition, scope of works and working schedule regulative documents of those Inter-Agency Working Groups have been discussed and approved by all members. Risk of low level cooperation between national and sub-national executing agencies was significantly reduced.
Critical Risks Affecting Progress (Not identified at project design) None
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
N/A | N/A | N/A
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Doppler water meters and 8 automated meteorological stations installed (Outcome 1) |  | Locations of 8 automated meteo stations and 2 Doppler water meters identified and design, configuration and specifications of water balance controlling facilities (weirs) developed |  | Locations of 8 hydrometeorological stations to be automated are identified and documented (Protocol signed by Head of Regional Administration on Hydrometeorlogical Services in Karakalpakstan) based on intensive consultations conducted. Design, configuration and specifications of water balance controlling facilities (weirs) developed by national consultant and is used for establishing firm baseline to identify water saving and agro conservation technologies /techniques impacts and benefits. | S
| At least 40,000 km2 of the Karakalpakstan region covered by automated hydro-meteorological observation network (Outcome 1) |  | Technical requirements for IT equipment required for automatization of hydro-meteorological observation network developed and IT equipment procured (20 medium capability computers, 10 high capability computers, including 2 high capability server) |  | Specifications and configuration of the automated observational network IT supportive equipment required for meeting current and anticipated climate and hydrometerological service demand, and securing non-interrupted data exchange developed by a national consultant. 20 computers with medium capacity, 10 high capacity computers, and 2 high capacity servers are being procured. | MS
| Season ahead forecasts and 2 weeks ahead temperature forecasts for effective warnings are practiced (Outcome 1) |  | Data input for Drought Early Warning System (DEWS) and calculation of drought indices identified and calculated |  | Data input required for DEWS and calculation of drought indices identified and calculated by a national consultant. This is the first step towards adjusting the existing DEWS to Amudarya river downstream conditions | S
| At least 40% of Dekhkan farmers and pastoralists of Karakalpak region are served by science-based extension (Outcome 1) |  | Needs of framers and dekhans in providing climate change adaptation focused extension services identified |  | Only initial steps were undertaken so far within the project Inception Phase. 3 introductory meetings were held with the Chair and representatives of the Council (Kengash) of Farmers in Karakalpakstan in Nukus, and its branches in Kegeli and Konlykul districts (project pilots). They were attended by farmers (only man-led farms) dealing with crop growing. Initial feedback has been collected. Next, project will undertake a number of meetings with pastoralists (livestock breeding farmers), woman-led framers and pastoralists (if available), science-based institutions that can provide extension services, to collect required for a more comprehensive needs assessment; learn best practices and experience; and formulate the needs (common and specifically related to farmers, pastoralists at gender mainstreaming approach). Needs assessment report will be produced within next reporting period. | MS
| At least 3 Field School/Extension established and delivered training in adaptation practices to farmers and pastoralists (Outcome 1) |  | Needs in IT equipment to support Extension Centers identified |  | Needs in IT equipment to support Extension Centers identified, and corresponding IT equipment configuration and specifications developed | S
| At least 20% of targeted Dekhkan beneficiaries are female (Outcome 1) |  | Relevant central, regional and local women organizations and/or NGOs identified. Their needs and capacities are assessed to be part of climate adaptation interventions /measures /practices to benefit from and increase their climate change resilience |  | During those consultations with farmers dealing with crops growing conducted so far within the project Inception Phase, 21% of the farmers were female (3 women of 11 men in Kegely district and 2 women of 12 men in Konlykul district) | MS
| At least 40,000 Dekhan farmers have adopted climate resilient conservation agriculture practices (Output 2.1) |  | Draft publication on greenhouse techniques as one of alternative water saving and livelihood diversification measures is prepared for farmers and local communities |  | Currently, review on greenhouse farming as one of alternative water saving practice and income raising measure conducted. It will serve as a ground for drafting publication by national consultant by May 2015 | MS
| At least 40,000 Dekhan farmers have adopted water saving irrigation practices (Output 2.2) |  | Needs of stakeholders in trainings on water saving techniques as well as their formats and terms identified |  | Initial discussions have been conducted within the same 3 introductory meetings held with the Chair and representatives of the Council (Kengash) of Farmers in Karakalpakstan in Nukus, and its branches in Kegeli and Konlykul districts (project pilots). Initial feedback on needs in trainings on water saving techniques as well as their applicable formats and terms collected from farmers (men-led farmers only). However, this issue was touched upon during the meeting with the Chair of State Women's Committee held in Tashkent. Next, needs assessment will be carried out in conjunction with the needs assessment for science-based extension support (Outcome 1). Final report will be prepared during the next reporting period. | MS
| Female lead horticulture greenhouses established (Outcome 2) |  | Needs of stakeholders in trainings on horticulture greenhouse establishing identified |  | The needs assessment is being done in conjunction with those for water saving measures and science-based extension services. Only initial discussions have taken place and a more comprehensive assessment is expected during the next reporting cycle. | MS
| Laws on agricultural practices and water management amended and integrate conservation agriculture and water saving techniques by the end of the third year |  | N/A as corresponding activities will be initiated during the second year of project implementation |  | N/A as corresponding activities will be initiated during the second year of project implementation | N/A
| Over 70,000 ha of arid land of Karakalpakstan is covered with saksaul and tamarix plantations and deliver sand stabilization and soil desalinization function (Outcome 3) |  | Four high precision differential GPS procured |  | Four high precision differential GPS procured | HS
| At least 20,000 people organized in at least 10 cooperatives at the khokimiyat and makhalla levels and participate in sand stabilization plantation scheme (Outcome 3) |  | At least one consultations on community management scheme for planting and maintenance as community employment scheme for landscape level adaptation with representatives of relevant organizations, farmers and local communities conducted, and outline of the scheme designed |  | Two consultations with Karakalpak Department of Center for supporting entrepreneurs and farmers of Uzbekistan, and Council (Kengash) of Farmers in Karakalpakstan were held to revisit the concept of a community employment scheme for landscape management. However, more consultations are required with farmers and pastoralists, dekhans and households, local communities and their self-governments and makhallas, local authorities (khokimiyats), and financial institutions to design a manageable and sustainable plan for of sand stabilization plantation scheme. | MS
| At least 10 community organizations (at least 5 female groups and village organizations) at khokimiyat and makhalla level have clear mandates, institutional capacities and skills and manage saksaul and tamarix plantations |  | At least two consultations with representatives of relevant organizations, farmers and local communities held, and needs in technical assistance for establishing cooperative management system for landscape rehabilitation and management identified |  | None of consultations has been held so far. Just an initial mapping of relevant organizations, farmers and local communities as well other relevant stakeholders is under development by national consultant. Such type of local community organization has never been considered, developed and piloted in Uzbekistan, and it requires more ground studies and learning of best practices implemented internationally but can be adjusted to the country's environment. | MS
| At least two sets of lessons learned bulletins produced and covered successful climate resilient agronomic and water saving measures (Outcome 4) |  | N/A as corresponding activities will be initiated during the second year of project implementation |  | N/A as corresponding activities will be initiated during the second year of project implementation | N/A
| At least 5 farmland demonstration meetings covered by the local and national media for adaptation advocacy (Outcome 4) |  | Formats and terms of 2 farm and pasture land demonstration meetings identified |  | Outline of formats and terms of 2 farm and pasture land demonstration meetings elaborated by project team based on available knowledge and understanding. However, none of farmland demonstration meetings have been held so far as no demonstration activities have taken place so far. Moreover, outline designed shall be shared with national and UNDP PR experts to meet the national and UNDP's corporate requirements for press and media coverage. | MS
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Aleksandr Merkushkin
| Email: | aleksandr.merkushkin@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
This is the first progress report since the inception of the project (October 2014). Despite a relatively short reporting period, the project team has successfully conducted a number of preparatory steps to put the project on track for accelerated implementation during the next reporting period. Some of these steps include: - Two Inter Agency Working groups (national and sub-national) established to support M&E mechanism and smooth project implementation; - NPC and National Implementing Agency identified; - Two field trips to the project pilot sites were undertaken to conduct the extended meetings with both authorities and farmers; - Two Inception Workshops (in Tashkent and Nukus) conducted and covered by local and national media; - Core project staff hired (PM, AFA and NFC); - The project annual plan of activities developed. - Contracts with companies and individual consultants signed (They include procurement of automated hydrometeorological network supportive IT equipment and office IT equipment, differential GPS; and consultants working on technical specifications of automated hydrometeorological network supportive IT equipment and IT equipment for Extension Centers; collection of Drought Early Warning system data input and calculation of drought indices; development of design, specifications and installation of guide water balance controlling devices (weirs); development of draft publication on greenhouse use by farming as a tool for climate change adaptation and income raising) However, the project implementation was not without challenges. They include the following: - Delays during the project inception phase due to the need of passing the mandatory national endorsement procedures applied to any international project; - Delays associated with hiring of core project staff due to the internal CO UNDP procedures; To overcome these challenges (or recover from delays) the following steps are going to be undertaken: - Strengthening relationship between project core staff and project stakeholders through the in situ work of National Field Coordinator with local authorities, farmers and local communities; - Hiring two Task Managers (SC contract) to provide assistance on the dissemination of agro-techniques and conservation agricultural practices and landscape adaptation activities (Components 2 and 3); - Ensuring meeting the requirements on evidence based results achieved through water saving and agro- conservation technologies to establish a firm baseline to monitor impacts/benefits of their applications
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Doppler water meters and 8 automated meteorological stations installed (Outcome 1) |  | Locations of 8 automated meteo stations and 2 Doppler water meters identified and design, configuration and specifications of water balance controlling facilities (weirs) developed |  | Locations of 8 hydrometeorological stations to be automated are identified and documented (Protocol signed by Head of Regional Administration on Hydrometeorlogical Services in Karakalpakstan) based on intensive consultations conducted. Design, configuration and specifications of water balance controlling facilities (weirs) developed by national consultant and is used for establishing firm baseline to identify water saving and agro conservation technologies /techniques impacts and benefits. | S
| At least 40,000 km2 of the Karakalpakstan region covered by automated hydro-meteorological observation network (Outcome 1) |  | Technical requirements for IT equipment required for automatization of hydro-meteorological observation network developed and IT equipment procured (20 medium capability computers, 10 high capability computers, including 2 high capability server) |  | Specifications and configuration of the automated observational network IT supportive equipment required for meeting current and anticipated climate and hydrometerological service demand, and securing non-interrupted data exchange developed by a national consultant. 20 computers with medium capacity, 10 high capacity computers, and 2 high capacity servers are being procured. | MS
| Season ahead forecasts and 2 weeks ahead temperature forecasts for effective warnings are practiced (Outcome 1) |  | Data input for Drought Early Warning System (DEWS) and calculation of drought indices identified and calculated |  | Data input required for DEWS and calculation of drought indices identified and calculated by a national consultant. This is the first step towards adjusting the existing DEWS to Amudarya river downstream conditions | S
| At least 40% of Dekhkan farmers and pastoralists of Karakalpak region are served by science-based extension (Outcome 1) |  | Needs of framers and dekhans in providing climate change adaptation focused extension services identified |  | Only initial steps were undertaken so far within the project Inception Phase. 3 introductory meetings were held with the Chair and representatives of the Council (Kengash) of Farmers in Karakalpakstan in Nukus, and its branches in Kegeli and Konlykul districts (project pilots). They were attended by farmers (only man-led farms) dealing with crop growing. Initial feedback has been collected. Next, project will undertake a number of meetings with pastoralists (livestock breeding farmers), woman-led framers and pastoralists (if available), science-based institutions that can provide extension services, to collect required for a more comprehensive needs assessment; learn best practices and experience; and formulate the needs (common and specifically related to farmers, pastoralists at gender mainstreaming approach). Needs assessment report will be produced within next reporting period. | MS
| At least 3 Field School/Extension established and delivered training in adaptation practices to farmers and pastoralists (Outcome 1) |  | Needs in IT equipment to support Extension Centers identified |  | Needs in IT equipment to support Extension Centers identified, and corresponding IT equipment configuration and specifications developed | MS
| At least 20% of targeted Dekhkan beneficiaries are female (Outcome 1) |  | Relevant central, regional and local women organizations and/or NGOs identified. Their needs and capacities are assessed to be part of climate adaptation interventions /measures /practices to benefit from and increase their climate change resilience |  | During those consultations with farmers dealing with crops growing conducted so far within the project Inception Phase, 21% of the farmers were female (3 women of 11 men in Kegely district and 2 women of 12 men in Konlykul district) | MS
| At least 40,000 Dekhan farmers have adopted climate resilient conservation agriculture practices (Output 2.1) |  | Draft publication on greenhouse techniques as one of alternative water saving and livelihood diversification measures is prepared for farmers and local communities |  | Currently, review on greenhouse farming as one of alternative water saving practice and income raising measure conducted. It will serve as a ground for drafting publication by national consultant by May 2015 | MS
| At least 40,000 Dekhan farmers have adopted water saving irrigation practices (Output 2.2) |  | Needs of stakeholders in trainings on water saving techniques as well as their formats and terms identified |  | Initial discussions have been conducted within the same 3 introductory meetings held with the Chair and representatives of the Council (Kengash) of Farmers in Karakalpakstan in Nukus, and its branches in Kegeli and Konlykul districts (project pilots). Initial feedback on needs in trainings on water saving techniques as well as their applicable formats and terms collected from farmers (men-led farmers only). However, this issue was touched upon during the meeting with the Chair of State Women's Committee held in Tashkent. Next, needs assessment will be carried out in conjunction with the needs assessment for science-based extension support (Outcome 1). Final report will be prepared during the next reporting period. | MS
| Female lead horticulture greenhouses established (Outcome 2) |  | Needs of stakeholders in trainings on horticulture greenhouse establishing identified |  | The needs assessment is being done in conjunction with those for water saving measures and science-based extension services. Only initial discussions have taken place and a more comprehensive assessment is expected during the next reporting cycle. | MS
| Laws on agricultural practices and water management amended and integrate conservation agriculture and water saving techniques by the end of the third year |  | N/A as corresponding activities will be initiated during the second year of project implementation |  | N/A as corresponding activities will be initiated during the second year of project implementation | N/A
| Over 70,000 ha of arid land of Karakalpakstan is covered with saksaul and tamarix plantations and deliver sand stabilization and soil desalinization function (Outcome 3) |  | Four high precision differential GPS procured |  | Four high precision differential GPS procured | S
| At least 20,000 people organized in at least 10 cooperatives at the khokimiyat and makhalla levels and participate in sand stabilization plantation scheme (Outcome 3) |  | At least one consultations on community management scheme for planting and maintenance as community employment scheme for landscape level adaptation with representatives of relevant organizations, farmers and local communities conducted, and outline of the scheme designed |  | Two consultations with Karakalpak Department of Center for supporting entrepreneurs and farmers of Uzbekistan, and Council (Kengash) of Farmers in Karakalpakstan were held to revisit the concept of a community employment scheme for landscape management. However, more consultations are required with farmers and pastoralists, dekhans and households, local communities and their self-governments and makhallas, local authorities (khokimiyats), and financial institutions to design a manageable and sustainable plan for of sand stabilization plantation scheme. | MS
| At least 10 community organizations (at least 5 female groups and village organizations) at khokimiyat and makhalla level have clear mandates, institutional capacities and skills and manage saksaul and tamarix plantations |  | At least two consultations with representatives of relevant organizations, farmers and local communities held, and needs in technical assistance for establishing cooperative management system for landscape rehabilitation and management identified |  | None of consultations has been held so far. Just an initial mapping of relevant organizations, farmers and local communities as well other relevant stakeholders is under development by national consultant. Such type of local community organization has never been considered, developed and piloted in Uzbekistan, and it requires more ground studies and learning of best practices implemented internationally but can be adjusted to the country's environment. | MS
| At least two sets of lessons learned bulletins produced and covered successful climate resilient agronomic and water saving measures (Outcome 4) |  | N/A as corresponding activities will be initiated during the second year of project implementation |  | N/A as corresponding activities will be initiated during the second year of project implementation | N/A
| At least 5 farmland demonstration meetings covered by the local and national media for adaptation advocacy (Outcome 4) |  | Formats and terms of 2 farm and pasture land demonstration meetings identified |  | Outline of formats and terms of 2 farm and pasture land demonstration meetings elaborated by project team based on available knowledge and understanding. However, none of farmland demonstration meetings have been held so far as no demonstration activities have taken place so far. Moreover, outline designed shall be shared with national and UNDP PR experts to meet the national and UNDP's corporate requirements for press and media coverage. | MS
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Yusuke Taishi; Rano Baykhanova
| Email: | yusuke.taishi@undp.org; rano.baykhanova@undp.org
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The overall rating is Marginally Satisfactory. The positive trend is that building of partnership with all key government agencies, parliament, NGOs has been initiated through both official procedures and informal activities (mass media, UNDP and Uzhydromet websites, distribution of project one pagers, attending in relevant meetings and round-tables). However, less activities has been undertaken at rural communities level, as this requires full project team on board and having National Field Coordinator on board in Karakalpakstan. Some on-going UNDP projects (to be completed in 2015) have established a sound ground and is enabling achieving the project Outcomes 1 and 2: DEWS functioning, establishing Extension Service Centers, greenhouses with drip irrigation and use of land laser leveling (water efficient practices) were tested and piloted at sub-national level (Kashkadarya province) within UNDP project "Climate Risk Management in Uzbekistan"; and use of PVs have been demonstrated in rural medical facilities in Karakalpakstan as an option to deploy the applicable RES options within UN Joint Programme in Karakalpakstan. Achieving the Outcome 3 can require testing a completely mew mechanisms (e.g. local cooperatives supported by local authorities) though some very limited activities related growing ingenious plants (saxaul and tamarisk) were demonstrated. Outcome 4 is crucial for generating and codifying knowledge and expertise on adaptation practices a well its effective and efficient sharing and dissemination among all stakeholders. Project Manager has develop a corresponding strategy and Action Plan as well as hiring professional PR expert to manage communication activities, producing knowledge products, and establishing publicly accessible knowledge sharing platform(s). The project incurred a delay (vs the planned initially for the first year) due to the need to pass through the mandatory national approval process applied by the Government to all international donor funded projects but also due to delays in the recruitment of the core project team (some staff such as AFA was not selected during the first round due to lack of suitable candidates). Unavailability of national consultants specialized in adaptation (identified national experts are civil servants working in Uzhydromet) will continue to pose a risk of a prolonged recruitment process in the future. This risk will be mitigated through establishing close synergy and cooperation with other international and national projects such as UNDP/GEF, WB, USAID, ADB projects, etc. with coordination and guidance from the UNDP Country Office. Another risk relates to seasonal nature of some activities to be implemented at landscape level (e.g. planting of shrubs, their watering, etc.), land laser leveling, construction and use of greenhouses that shall be taken into account during annual planning (timely procurement of equipment and hiring of national/international consultants). Delivery of funds allocated through the first tranche has been secured through development of detailed Plan of Activities with assistance of Environment and Energy Unit (EEU), as well as its close monitoring by Focal Point in EEU, Resource Monitoring Unit and M&E Officer in UNDP CO.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other: National Partner Implementing Agency, Uzhydromet | Doppler water meters and 8 automated meteorological stations installed (Outcome 1) |  | Locations of 8 automated meteo stations and 2 Doppler water meters identified and design, configuration and specifications of water balance controlling facilities (weirs) developed |  | Locations of 8 hydrometeorological stations to be automated are identified and documented (Protocol signed by Head of Regional Administration on Hydrometeorlogical Services in Karakalpakstan) based on intensive consultations conducted. Design, configuration and specifications of water balance controlling facilities (weirs) developed by national consultant and is used for establishing firm baseline to identify water saving and agro conservation technologies /techniques impacts and benefits. | S
| At least 40,000 km2 of the Karakalpakstan region covered by automated hydro-meteorological observation network (Outcome 1) |  | Technical requirements for IT equipment required for automatization of hydro-meteorological observation network developed and IT equipment procured (20 medium capability computers, 10 high capability computers, including 2 high capability server) |  | Specifications and configuration of the automated observational network IT supportive equipment required for meeting current and anticipated climate and hydrometerological service demand, and securing non-interrupted data exchange developed by a national consultant. 20 computers with medium capacity, 10 high capacity computers, and 2 high capacity servers are being procured | MS
| Season ahead forecasts and 2 weeks ahead temperature forecasts for effective warnings are practiced (Outcome 1) |  | Data input for Drought Early Warning System (DEWS) and calculation of drought indices identified and calculated |  | Data input required for DEWS and calculation of drought indices identified and calculated by a national consultant. This is the first step towards adjusting the existing DEWS to Amudarya river downstream conditions | MS
| At least 40% of Dekhkan farmers and pastoralists of Karakalpak region are served by science-based extension (Outcome 1) |  | Needs of framers and dekhans in providing climate change adaptation focused extension services identified |  | Only initial steps were undertaken so far within the project Inception Phase. 3 introductory meetings were held with the Chair and representatives of the Council (Kengash) of Farmers in Karakalpakstan in Nukus, and its branches in Kegeli and Konlykul districts (project pilots). They were attended by farmers (only man-led farms) dealing with crop growing. Initial feedback has been collected. Next, project will undertake a number of meetings with pastoralists (livestock breeding farmers), woman-led framers and pastoralists (if available), science-based institutions that can provide extension services, to collect required for a more comprehensive needs assessment; learn best practices and experience; and formulate the needs (common and specifically related to farmers, pastoralists at gender mainstreaming approach). Needs assessment report will be produced within next reporting period. | MS
| At least 3 Field School/Extension established and delivered training in adaptation practices to farmers and pastoralists (Outcome 1) |  | Needs in IT equipment to support Extension Centers identified |  | Needs in IT equipment to support Extension Centers identified, and corresponding IT equipment configuration and specifications developed | MS
| At least 20% of targeted Dekhkan beneficiaries are female (Outcome 1) |  | Relevant central, regional and local women organizations and/or NGOs identified. Their needs and capacities are assessed to be part of climate adaptation interventions /measures /practices to benefit from and increase their climate change resilience |  | During those consultations with farmers dealing with crops growing conducted so far within the project Inception Phase, 21% of the farmers were female (3 women of 11 men in Kegely district and 2 women of 12 men in Konlykul district) | MS
| At least 40,000 Dekhan farmers have adopted climate resilient conservation agriculture practices (Output 2.1) |  | Draft publication on greenhouse techniques as one of alternative water saving and livelihood diversification measures is prepared for farmers and local communities |  | Currently, review on greenhouse farming as one of alternative water saving practice and income raising measure conducted. It will serve as a ground for drafting publication by national consultant by May 2015 | S
| At least 40,000 Dekhan farmers have adopted water saving irrigation practices (Output 2.2) |  | Needs of stakeholders in trainings on water saving techniques as well as their formats and terms identified |  | Initial discussions have been conducted within the same 3 introductory meetings held with the Chair and representatives of the Council (Kengash) of Farmers in Karakalpakstan in Nukus, and its branches in Kegeli and Konlykul districts (project pilots). Initial feedback on needs in trainings on water saving techniques as well as their applicable formats and terms collected from farmers (men-led farmers only). However, this issue was touched upon during the meeting with the Chair of State Women's Committee held in Tashkent. Next, needs assessment will be carried out in conjunction with the needs assessment for science-based extension support (Outcome 1). Final report will be prepared during the next reporting period. | MS
| Female lead horticulture greenhouses established (Outcome 2) |  | Needs of stakeholders in trainings on horticulture greenhouse establishing identified |  | The needs assessment is being done in conjunction with those for water saving measures and science-based extension services. Only initial discussions have taken place and a more comprehensive assessment is expected during the next reporting cycle. | MS
| Laws on agricultural practices and water management amended and integrate conservation agriculture and water saving techniques by the end of the third year |  | N/A as corresponding activities will be initiated during the second year of project implementation |  | N/A as corresponding activities will be initiated during the second year of project implementation | N/A
| Over 70,000 ha of arid land of Karakalpakstan is covered with saksaul and tamarix plantations and deliver sand stabilization and soil desalinization function (Outcome 3) |  | Four high precision differential GPS procured |  | Four high precision differential GPS procured | S
| At least 20,000 people organized in at least 10 cooperatives at the khokimiyat and makhalla levels and participate in sand stabilization plantation scheme (Outcome 3) |  | At least one consultations on community management scheme for planting and maintenance as community employment scheme for landscape level adaptation with representatives of relevant organizations, farmers and local communities conducted, and outline of the scheme designed |  | Two consultations with Karakalpak Department of Center for supporting entrepreneurs and farmers of Uzbekistan, and Council (Kengash) of Farmers in Karakalpakstan were held to revisit the concept of a community employment scheme for landscape management. However, more consultations are required with farmers and pastoralists, dekhans and households, local communities and their self-governments and makhallas, local authorities (khokimiyats), and financial institutions to design a manageable and sustainable plan for of sand stabilization plantation scheme. | MS
| At least 10 community organizations (at least 5 female groups and village organizations) at khokimiyat and makhalla level have clear mandates, institutional capacities and skills and manage saksaul and tamarix plantations |  | At least two consultations with representatives of relevant organizations, farmers and local communities held, and needs in technical assistance for establishing cooperative management system for landscape rehabilitation and management identified |  | None of consultations has been held so far. Just an initial mapping of relevant organizations, farmers and local communities as well other relevant stakeholders is under development by national consultant. Such type of local community organization has never been considered, developed and piloted in Uzbekistan, and it requires more ground studies and learning of best practices implemented internationally but can be adjusted to the country's environment. | MS
| At least two sets of lessons learned bulletins produced and covered successful climate resilient agronomic and water saving measures (Outcome 4) |  | N/A as corresponding activities will be initiated during the second year of project implementation |  | N/A as corresponding activities will be initiated during the second year of project implementation | N/A
| At least 5 farmland demonstration meetings covered by the local and national media for adaptation advocacy (Outcome 4) |  | Formats and terms of 2 farm and pasture land demonstration meetings identified |  | Outline of formats and terms of 2 farm and pasture land demonstration meetings elaborated by project team based on available knowledge and understanding. However, none of farmland demonstration meetings have been held so far as no demonstration activities have taken place so far. Moreover, outline designed shall be shared with national and UNDP PR experts to meet the national and UNDP's corporate requirements for press and media coverage. | MS
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Prof. Victor Chub, National Project Coordinator of Adaptation Project in Uzbekistan
| Email: | Uzhymet@meteo.uz
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The overall rating is Marginally Satisfactory due to the forced delay of project Implementation mainly caused by the need to pass through the required national approval process applied to all international donor funded projects. Also operational issues related to hiring the core project team hindered all along the Project Inception phase. The latter also affected implementation of the planned thematic activities. Spite of those issues project staff with help of Head of EEU, Climate Change Specialist (Focal Point for the project in EEU) and cooperation with project stakeholder was able to keep project pace the way to achieve main targets identified for this reporting period. Among them the following points should be noted: - Cooperation with national and sub national stakeholders will be involved in autoimmunization of the existing meteo stations established; - Initial screening of needs to improve hydro-meteorological observation network conducted; - One international practice on agronomic and effective water and land management documented and shared with project partners. To enhance project management capacity and improve project implementation, it would be recommended to hire Task Managers for each thematic components of the project but two Task Managers for Components 2 and 3 are the priority ones to be hired. It is also recommended to consider a possibility for automatization of all 10 existing hydrometeorological stations versus 8 ones initially planned within the budget allocated as per Project Document for procurement of required equipment.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1 | Indicator 1.1.1: Number of automated met stations for field data collection and transmission | Currently, there is no automated hydro-meteorological stations in Karakalpakstan | Design, configuration and specifications of water balance controlling facilities (weirs) developed and identified. | 8 automated hydro-meteorological stations and 2 Doppler water meters installed
| Indicator 1.2.1: Coverage of hydro-meteorological observation network on km2 | Currently, there is no spatial coverage of automated hydro-meteorological observation network | Location of 8 automated hydrometeorological equipment identified to cover 40,000 km2 of Karakalpakstan region. | At least 40,000 km2 of the Karakalpakstan region covered by automated hydro-meteorological observation network
| Indicator 1.3.1: Lead time for drought early warning | Currently, drought early warning does not exists | Consultations with National Project Coordinator, experts from sub-national hydrometerological service administration and other stakeholders conducted to assess IT support and equipment needs for continuous hydrometeorological data acquisition, monitoring and control as well as data input to drought early warning system and weather forecasting system | Seasonal and biweekly
| Indicator 1.4.1: % Dekhkan farmers (% female Dekhkan farmers) receiving extension services to introduce farm-based climate risk management measures | Uzbekistan does not yet have a science-based extension system in place | First, the most vulnerable districts to be targeted in the project were selected after three rounds of analysis: 1) analysis of official statistical data on several factors of vulnerability; 2) verification of the official data through consulting local authorities local residents; and 3) construction of a vulnerability index. As a result, three districts have been identified and at least one Extension Services Center will be established in each district. Second, community consultations have been initiated to identify farmers needs in terms of extension services and their preferred forms of receiving them. The consultations are still ongoing and will be continued in the next reporting cycle. | At least 40% of Dekhkan farmers and pastoralists of Karakalpakstan region served by science-based extension
| Indicator 1.4.2: # of Field School/Extension delivering training in adaptation practices to farmers and pastoralists. | Currently, no Field School/Extension outlets exist in Karakalpakstan | The consultations with farmers and heads of local Kengash (council) of farmers undertaken during the project inception phase in three target districts to verify farmers' needs. | At least 3 Field School/Extension established to deliver training in adaptation practices to farmers and pastoralists by the fourth year (2017)
Outcome 2 | Indicator 2.1.1: # of dekhkan farmers adopted conservation agriculture practices (e.g. low till, mixed cropping, fodder production, and residue crop soil) | It is estimated that 7-10% of farmers practice climate resilient conservation agriculture practices | N/A as corresponding activities will be initiated during the second year of project implementation | At least 40,000 Dekhan farmers have adopted climate resilient conservation agriculture practices
| Indicator 2.2.1: # of dekhkan farmers adopted water saving irrigation practices (e.g. land levelling, furrow and drip irrigation systems) | It is estimated that 3-5% of farmers practice water saving practices | N/A as corresponding activities will be initiated during the second year of project implementation | At least 40,000 Dekhan farmers have adopted water saving irrigation practices
| Indicator 2.3.1: Number of female lead horticulture greenhouses established | In Karakalpakstan, currently no horticulture greenhouses are led by women farmers (This is currently being verified as part of inception phase activities) | Initial consultations with a few representatives of female farmers revealed that one of the barriers to a widespread use of greenhouse is lack of information about its benefits, and to address it, information products would be helpful for an increased take up. In the next reporting cycle, consultations with wider groups of female farmers will continue to understand needs specific to female farmers. | At least five woman-led horticulture greenhouses established by end of second year (out of 12 greenhouses that will be delivered in the project)
| Indicator 2.4.1: # of legal acts and regulations enacted to support well tested farm-based adaptation measures. | Legal acts and regulations that exist do not provide conditions that facilitate take-up of farm-based adaptation | An initial knowledge exchange dialogue has started with projects with similar focus such as Climate Risk Management Project, Disaster Risk Reduction Project, and Integrated Water Resources Management for obtaining their experiences in improving legislations related to agriculture and water management. | At least three laws/regulations on agricultural practices and water management amended and integrated regulations on the adoption of conservation agriculture and water saving techniques and technologies on the farms by end of the third year
Outcome 3 | Indicator 3.1.1: # of ha with saksaul and tamarix plantations to deliver sand stabilization and soil desalinization function. | There have been only sporadic and largely unsuccessful attempts of sand stabilization | Informal consultations with representatives of Oblast Administration of Nature Protection, State Administration on Forestry in Nukus (under Ministry of Agriculture and Water Resources) and Karakalpak Department of Center supporting entrepreneurs and farmers of Uzbekistan on landscape adaptation management plan initiated | Over 70,000 ha of arid land of Karakalpakstan is covered with saksaul and tamarix plantations and deliver sand stabilization and soil desalinization function
| Indicator 3.2.1: # of Dekhkan farmer and pastoral community members involved in landscape level adaptation measures (e.g. saksaul and tamarix planting) through local employment programme. | Currently, there is no systemic engagement of dekhan farmers and pastoral community for landscape land management | Initial awareness raising dialogue on the need of establishing cooperative management of sand stabilization measures at the khokimiyat and makhalla level was initiated during the inception phase with relevant organizations. | At least 20,000 people organized in at least 10 cooperatives at the khokimiyat and makhalla levels and participate in sand stabilization plantation scheme
| Indicator 3.3.1: # of cooperatives established at Khokimiyat and Makhalla levels for community management of sand stabilising plantations. | Cooperatives are a new mechanism that has not been tested in the country, and hence, there is currently none. | During Informal consultations with Chair of Women Committee of Uzbekistan, the needs of local institutions for improving and strengthening existing mandates, skills and institutional capacities were briefly discussed, including possible ways of improving the involvement of women into landscape adaptation activities | At least 10 community organizations (at least 5 female groups and village organizations) at khokimiyat and makhalla level have clear mandates, institutional capacities and skills and manage saksaul and tamarix plantations by end of the fourth year
Outcome 4 | Indicator 4.1.1: # of documented good practices of agronomic and water saving measures. | None | No significant activities on this indicator have started. | At least two sets of bulletins published including information about results of inventory of all tested agronomic and water saving measures and successful practices mapped out
| Indicator 4.2.1: # of lessons learned bulletins disseminated through printed and web-based media. | None | No significant activities on this indicator have started. | At least two sets of lessons learned bulletins produced covering successful climate resilient agronomic and water saving measures
| Indicator 4.3.1: # of farm and pasture land demonstration meetings covered by media and attended by national and local authorities | None | No significant activities on this indicator have started. | At least 5 farmland demonstration meetings covered by the local and national media for adaptation advocacy

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Although the project implementation period for this report is only about 5 months, the following lessons have been learned: - Development of an annual work plan is a powerful tool to accelerate project implementation and increase its efficiency; - During the planning of project activities, a lag time needs to be considered for operational/administrative procedures for each activity so that activities are carried out in a realistic manner; - National and sub-national authorities welcomed the Inter-Agency Working Groups designated by Government to facilitate cross-ministerial knowledge exchange on project activities and ensure alignment between project activities and national priorities; - The Project Manager benefited from a training organized by UNDP targeting project managers working on climate change adaptation. Investments in capacity building for project-financed staff are often overlooked but extremely important to ensure that both operational and substantive challenges are sufficiently addressed. This event was important for south-south knowledge exchange as well. At the national policy and institutional level, Uzbekistan suffers from a lack of a nationwide legal framework on climate change as well as a mechanism for information exchange on climate change. Moreover, the decision-making process for integrating adaptation measures into the national and sectoral plans and regional development strategy is complex, preventing the Government from mainstreaming the issue into the existing development discussion. Although this Adptation Fund project is not specifically designed to address this issue, it is expected that the project can contribute to filling some of the existing gaps through raising awareness among key decision makers including the Council of Ministers in Karakalpakstan, its Parliament, sub-national and sectoral ministries and agencies, regional and local administrations, and local self-government. Moreover, climate change related official statistics and indicators shall be available and widely publicly accessible not only for government agencies but in the appropriate and reasonable format for population to promote climate adaptation interventions.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Yes. The delays were primarily due to the government approval processes, both at the national and regional level, that were required for all projects supported by international donor organizations. At the national level, the approval from the Cabinet of Ministers of the Republic of Uzbekistan was needed and the project was nationally endorsed by the Order of the Prime-Minister of Uzbekistan, #03/5-885 of 29.08.2014. At the regional level, the approval was required from the autonomous Republic of Karakalpakstan, namely Council of Ministers (Decree #213-b of 09.10.14.). These approvals and subsequent issuance of the Prime Ministerial Order and Decree were needed to appoint/recruit the National Project Coordinator and Project Manager. The speed of the approval process was out of the control of the project. However, despite the delay, such procedure ensures national ownership and commitments for timely and efficient project implementation in partnership with the national stakeholders. For example, the presence of the government order and decree enabled the establishment of the Inter-Agency Working Group, comprising representatives of key national and subnational agencies. Such an arrangement have proved instrumental in earlier projects implemented in the country (e.g. CA Climate Risk Management project, GEF funded projects, etc.)
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | No. During the project inception workshop, a review of the Project Results Framework was carried out with key stakeholders to verify whether the project outputs and activities are still relevant, assumptions still valid, and general development contexts in which this project takes place up-to-date. The consultation resulted in an agreement that the Project Results Framework, as approved by the Adaptation Fund Board, still remains relevant and no changes are required at this point.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Gender mainstreaming activities are essential part of all project activities/components as this is one of the priority focal areas for all: national authorities, UNDP and the Adaptation Fund. Project underwent a gender screening process as part of UNDP support and was rated as 1 (from the range of 0-3). It means that project outputs will contribute to some extent to increasing gender equality. The following were learnt from the screening process: - To establish baseline for analysing of climate change impacts particularly on women involved in farming and household activities and potential benefits that can be generated from climate adaptation measures undertaken relevant and reliable data to be collected; - To identify needs of women as well as corresponding barriers compared to men all collected data should be gender disaggregated ; - PR actions/campaigns including development of success stories emphasize role and promote involvement of women to conservation agriculture and adaptation interventions. Also the recommendations touched on a potential role of the Women’s Committee in the project implementation including the following: - Prepare gender-disaggregated farm profiles for project pilot sites; - Share best practice and lessons learned on new jobs creation for women farmers and graziers; - Assist with conceptualization of female-led horticulture greenhouses establishment and its operations; - Identify specific roles of women in cooperative management for sand stabilization measures at the khokimiyat and makhalla level; - Participate in dialog, in general, to promote effective participation of women in adaptation activities.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Please select the relevant Fund level Outcome and Output indicators that allign with the project objectives and outcomes
OBJECTIVE 1
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at project/programme approval (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 1 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 1 | Drought early warning information produced in Karakalpakstan (Seasonal and biweekly) | Currently Uzhydromet provides only weather forecasts (1-5 days, 1 month and seasonal) but drought early warning is not produced in Karakalpakstan.
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at project/programme approval | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 1 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 1.2 | 2 types of drought early warning (seasonal and biweekly) based on snow supply assessment through modeling and satellite photos as well as assessment of hydrographs | Currently, there is no drought early warning in Karakalpakstan
OBJECTIVE 2
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at project/programme approval (see Units in next sheet) | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 3 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 3.1 | 5 | 2-3
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at project/programme approval | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 3 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 3.1 | Farmers in Karakalpakstan (at least 40% of Dekhan farmers, of which 20% is female) receive agricultural extension support based on climate-science [In other words, one (1) number and one (1) type of risk reduction action] | None
OBJECTIVE 3
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at project/programme approval | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 6 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 6.1 | 4 | N/A
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at project/programme approval | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 6 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individual or community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 6.1 | One (1) each of two (2) types of adaptation knowledge asset created: One on conservation agriculture and another on water savings measures in the context of maintaining resilient livelihoods [Under each type, more specific investments can be provided at a later stage in the project implementation] | Currently, it is estimated that 35-40% of farmers are aware of conservation agriculture and water savings techniques; yet, they are practiced by 7-10% and 3-5% of farmers, respectively.
OBJECTIVE 4
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at project/programme approval | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 5 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 5 | 70,000 ha of arid land of Karakalpakstan is covered with plantations | There have been only sporadic and largely unsuccessful attempts of sand stabilization
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at project/programme approval | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 5 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 5 | The conditions of 70,000 ha of arid land are improved through plantations of saksaul and tamarix | There have been only sporadic and largely unsuccessful attempts of sand stabilization
OBJECTIVE 5
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at project/programme approval | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 3 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 3.1 | 5 | 2-3
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at project/programme approval | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 3 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 3.2 | At least two (2) sets of lessons learned bulletins produced | None

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.