## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 14 June 2012 - 31 May 2013
| Project Title: | Ecosystem Based Adaptation Approach to Maintaining Water Security in Critical Water Catchments in Mongolia
| Project Summary: | The Project's objective is to “maintain the water provisioning services supplied by mountain and steppe ecosystems by internalizing climate change risks within land and water resource management regimes.” This project applies the principles of Ecosystem-based Adaptation (EBA) to increase climate change resilience at a landscape level. EBA is broadly defined as “a range of local and landscape scale strategies for managing ecosystems to increase resilience and maintain essential ecosystem services and reduce the vulnerability of people, their livelihoods and nature in the face of climate change” (UNFCCC) Project investments will alleviate vulnerabilities and dismantle identified barriers by implementing three interconnected components: Component I: Integrated Strategies/Management Plans for target landscapes/river basins developed and under implementation. Component II: Implementing landscape level adaptation techniques to maintain ecosystem integrity and water security under conditions of climate change. Component III: Strengthening capacities/Institutions to support EbA strategies and integrated river basin management, their replication and mainstreaming in sector policies.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | 4505 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme - UNDP | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Mongolia | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | 1. The Altai Mountains and Great Lakes Basin Eco-region: Turgen/ Kharkhiraa Sub River Basins -Turgen, Ulaangom, Sagil, Bukhmurun, Khovd, Tarialan, Naranbulag soums of Uvs aimag 2. The Eastern Steppe Eco- region: Ulz River Basin- Chuluunkhoroot, Dashbalbar, Bayndun, Bayn-Uul, Gurvanzagal, Choibalsan, Sergelen soums of Dornod aimag, Bayn-Adarga, Batnorov, Norovlin soums of Khentii aimag | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2011-06-22
IE-AFB Agreement Signature Date: |  | 2011-11-03 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2012-06-14 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2014-06-14
| Terminal Evaluation Date: | 3 months prior to the final Project Board Meeting
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | 1. Reports: a) Inception report, b) Quarterly reports, c)Annual report, d) Project leaflet f) Soum level capacity needs assessment | Czech Republic
2. Advocacy materials: Quarterly Newsletters, table calendar 2013, 20 minute short video on climate change issues. WMO English comic on "We care for our climate" and GIZ English animation on "We know enough about climate change" was translated into Mongolian and duplicated.
3. Guidebook: a) "Climate change and adaptation-facilitating the Relations between Ecosystems and Humans" for policy makers, local communities, and general public; b)"Principles and methodologies of IRBM and associated training modules";c) Physical measures of EBA at local level, and associated training modules designed for different knowledge-level users.
4. Programme: a) Comprehensive Institutional Capacity Building Strategy for internalizing EBA approaches into development policy and planning of key agencies; b) Public Awareness Programme of EBA principles and practice c )Soum level capacity building programme.
| List the Website address (URL) of project. | 5. Regulations: In accordance with relevant Articles of Law of Water Pollution Fee: a) Article 4.5.-Proposal for the charge for waste water discharged from household usage (consumers); b) Article 5.2-Proposal for Regulation to define amount of charge for water pollution; c) Article 7.2-Proposal for regulation to specify list of economic entity and organizations, and to set the percentage of discount; In accordance of relevant Articles of Law of Forest a) 4.13-Proposal for Regulation of procedure for the payment to owner for forest protection, restoration and nursery in case of timbering woods according to the permission of state authorized organization; b) 10.2-Proposal for Regulation on commercial activities undertaken in special purpose forest area of the State; c) 39.2,3,4,5-Proposal for common regulation of incentives 6. A one-minute video documenting what the 79-year-old herder Mr Tseren Dashtseren witnessed over the years related to the environmental changes. 7. A case study on the project which has been included in the UNDP Biodiversity and Ecosystem Framework 2012-2020, published and launched in October 2012. 8. An essay competition on “what we should do to mitigate and adapt climate change” was organized successfully among university students. This competition was a great contribution for increasing public awareness of climate change and encouraging their active participation in climate change mitigation and adaptation. | Democratic People's Republic of Korea
|  | http://www.climatechange.gov.mn/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Tuya Tserenbataa | Dominican Republic
| Email: | tuya.tserenbataa@undp.org | Ecuador
| Date: | 2013-05-01 | Egypt
| Government DA |  | El Salvador
| Name: | Dagvadorj. D, Special Envoy for Climate Change, Director, Climate Change Coordination Office of MEGD | Equatoral Guinea
| Email: | d_dagvadorj@yahoo.com; dagvadorj@mne.gov.mn | Eritrea
| Date: | 2013-05-05 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Chimeg Junai, Programme Manager | Fiji
| Email: | chimeg.junai@undp.org | Finland
| Date: | 2013-05-10 | France
| Executing Agency |  | Gambia
| Name: | Oyun. S, Parliament member, Minister of Environment and Green Development | Georgia
| Email: | oyun@mne.gov.mn | Germany
| Date: | 2013-05-09 | Ghana
| Executing Agency |  | Greece
| Name: | Dagvadorj. D, Special Envoy for Climate Change, Director, Climate Change Coordination Office of MEGD | Grenada
| Email: | d_dagvadorj@yahoo.com, dagvadorj@mne.gov.mn | Guatemala
| Date: | 2013-05-05 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe
Note on D15: Doungjun Roongruang: This should refer to PIMS number 4505

## FinancialData
Financial information: cumulative from project start to 31 May 2013
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31 May 2013 | 525874
Add any comments on AF Grant Funds. (word limit=200) | Main reasons on lower delivery than expected are extended dates for service procurements due to unsufficient number qualified bidders that resulted shift of assessments to create benchmarks on ecological and socio-economy and cost and benefit of natural resources of the target areas to 2013. Therefore, key assessments to build on benchmarks such as vulnerability and risk assessments and feasibility studies on EbA local measures have also shifted to second half 2013 to be completed.
EXPENDITURE DATA
List item / activity / action and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Activity 1 | 175568.91
| Activity 2 | 109028.28
| Activity 3 | 129383.14
| Activity 4 | 108870.5
| Exchange loss | 3023.39
| TOTAL | 525874.22
PLANNED DISBURSEMENT SCHEDULE
List item / activity / action planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Activity 1 | 133717.1967 | 2014-05-31
| Activity 2 | 770313.62 | 2014-05-31
| Activity 3 | 299041.66 | 2014-05-31
| Activity 4 | 88470.2867 | 2014-05-31
| TOTAL | 1291542.7633
ACTUAL CO-FINANCING
How much of the total co-financing as committed in the Project Document has actually been realized? | N/A
If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Procurement
PROCUREMENT DATA
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
| Contract Type | Agency / Contracted party | Amount | Signature Date
| Purchase Order |  | 3117.60 lump sum | 2012-03-23
| Purchase Order |  | 2433.42 lump sum | 2012-03-26
| Purchase Order |  | 5460.33 lump sum | 2012-03-26
| Purchase Order |  | 1127.27 lump sum | 2012-04-25
| Purchase Order |  | 3090.42 lump sum | 2012-04-25
| Purchase Order |  | 198.67 lump sum | 2012-04-25
| Purchase Order |  | 1233.88 lump sum | 2013-05-09
| Purchase Order |  | 2755 lump sum | 2012-06-04
| Purchase Order |  | 268.58 lump sum | 2012-06-13
| Purchase Order |  | 407.63 lump sum | 2012-08-08
| Purchase Order |  | 934 lump sum | 2012-08-08
| Purchase Order |  | 327.49 lump sum | 2012-08-09
| Purchase Order |  | 2403.18 lump sum | 2012-08-09
| Purchase Order |  | 5252.75 lump sum | 2012-08-20
| Purchase Order |  | 2022.59 lump sum | 2012-08-29
| Purchase Order |  | 769.44 lump sum | 2012-09-21
| Purchase Order |  | 3250.32 lump sum | 2012-10-22
| Purchase Order |  | 17959.77 lump sum | 2012-11-09
| Purchase Order |  | 5373.77 lump sum | 2012-11-28
| Purchase Order |  | 660.50 lump sum | 2012-11-22
| Purchase Order |  | 356.25 lump sum | 2012-11-22
| Purchase Order |  | 222.58 lump sum | 2012-11-28
| Purchase Order |  | 204.25 lump sum | 2012-11-28
| Purchase Order |  | 1362 lump sum | 2012-12-04
| Purchase Order |  | 7355.05 lump sum | 2012-12-04
| Purchase Order |  | 3154.12 lump sum | 2012-12-05
| Purchase Order |  | 354.97 lump sum | 2012-12-05
| Purchase Order |  | 2264.8 lump sum | 2012-12-04
| Purchase Order |  | 1473.72 lump sum | 2012-12-17
| Purchase Order |  | 2312.73 lump sum | 2012-12-17
| Purchase Order |  | 1381.77 lump sum | 2012-12-28
| Purchase Order |  | 7800.21 lump sum | 2012-11-07
| Purchase Order |  | 860.43 lump sum | 2012-12-10
| Purchase Order |  | 1164.87 lump sum | 2012-12-05
| Purchase Order |  | 4874.77 lump sum | 2012-12-25
| Purchase Order |  | 6724.01 lump sum | 2012-12-05
| Purchase Order |  | 236.77 lump sum | 2012-12-25
| Purchase Order |  | 537.85 lump sum | 2012-12-25
| Purchase Order |  | 1199.80 lump sum | 2012-12-28
| Purchase Order |  | 1484.76 lump sum | 2013-01-31
| Purchase Order |  | 241.79 lump sum | 2013-02-28
| Purchase Order |  | 411.77 lump sum | 2013-03-20
| Purchase Order |  | 251.81 lump sum | 2013-04-04
| Purchase Order |  | 267.43 lump sum | 2013-04-22
| Purchase Order |  | 300.88 lump sum | 2013-04-24
| Purchase Order |  | 902.73 lump sum | 2013-05-22
| Service Contract |  | 1645.9 per month | 2012-01-30
| Service Contract |  | 1215.9 per month | 2012-02-01
| Service Contract |  | 1250 per month | 2012-05-01
| Service Contract |  | 610 per month | 2012-05-01
| Service Contract |  | 1120 per month | 2012-05-14
| Service Contract |  | 1450 per month | 2012-07-24
| Service Contract |  | 1450 per month | 2012-08-24
| Contract for services |  | 24708.45 lump sum | 2012-08-31
| Contract for services |  | 517.49 lump sum | 2012-09-17
| Service Contract |  | 1250 per month | 2012-10-01
| Contract for services |  | 114.7 lump sum | 2012-11-27
| Service Contract |  | 1911.08 per month | 2012-10-16
| Contract for services |  | 529.71 lupm sum | 2012-09-01
| Contract for services |  | 6777.58 lump sum | 2012-11-01
| Contract for services |  | 12,608.6 lump sum | 2012-12-01
| Contract for services |  | 8250 lump sum | 2012-12-01
| Service Contract |  | 680 per month | 2013-01-01
| Service Contract |  | 1250 per month | 2013-01-01
| Service Contract |  | 520 per month | 2013-01-07
| Service Contract |  | 1460 per month | 2013-02-01
| Contract for services |  | 267 lump sum | 2013-04-15
| Contract for services |  | 93.71 lump sum | 2013-04-24
| Contract for services |  | 41.64 lump sum | 2013-04-19
| Contract for services |  | 52.05 lump sum | 2013-04-18
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT | Submitted Bids |  | Bid amount | Justification | Winning Bid
Ecological and socio-economic baseline studies to be conducted in the Kharkhiraa/Turgen rivers basin; 25 Jul 2012 |  |  | 33808.5
|  |  | not opened | insufficient technical proposal
147713
|  |  | not opened | insufficient technical proposal
64845.4
|  |  | 28900 | Scored the highest in technical & financial evaluations
Ecological and socio-economic baseline studies to be conducted in the Ulz river basin; 25 Jul 2012 |  |  | 30008.5
|  |  | not opened | insufficient technical proposal
|  |  | not opened | insufficient technical proposal
|  |  | 28506.41 | Scored the highest in technical & financial evaluations
|  |  | not opened | insufficient technical proposal
28900
Design a Public Awareness Programme of EbA Principles and Practice; 31 Jul 2012 |  |  | 10133
18889
|  |  | 18430 | Scored the highest in technical & financial evaluations
Developing legislative documents accordance with law on payment for water pollution within the new package law on environment; 17 Sep 2012 |  |  | not opened | insufficient technical proposal
|  |  | 6410.26 | Scored the highest in technical & financial evaluations
Developing operational webpage of Climate Change & Ecosystem based Adaptation & Mitigation; 09 Aug 2012 |  |  | 11000
|  |  | 10000 | Scored the highest in technical & financial evaluations
Procurement for 6 vans; 29 Oct 2012 |  |  | 83212.9 | Scored the highest in technical & financial evaluations
170702.46
Climate change vulnerability and risk assessment in the Altai mountains/Great lakes depression and estimate the catchment surface and groundwater use balance in Turgen/ Kharkhiraa river basins; 16 Apr 2013 |  |  | 37000
|  |  | 20980.11 | Scored the highest in technical & financial evaluations
|  |  | not opened | insufficient technical proposal
92040
21492.8
Climate change vulnerability & risk assessment in the Eastern Steppe landscapes/Mongol Daguur & estimate the catchment surface & groundwater use balance in Ulz river basin; 16 Apr 2013 |  |  | 25777.3
|  |  | 16095.69 | Scored the highest in technical & financial evaluations
|  |  | not opened | insufficient technical proposal
28477

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them (word limit = 200)
Identified Risk | Current Status | Steps Taken to Mitigate Risk (as identified in the Prodoc)
Policy makers prioritize economic benefits over sustainable and resilient ecosystems | Impact: Moderately high (4); Probability: Low (1) | In order to ensure the government's understanding on climate change risk on ecosystem services and its impact on the economy, the Project supports an economic study. This study will quantify the economic impacts of envisaged ecological changes under the climate change conditions and measure the economics costs and benefits of alternative adaptation strategies to cope with these changes. The Project will develop an integrated model that links climate change to ecosystem changes and then economic changes. One component of the Project will study the effect of these changes on the supply and demand for water. The various sectors of the economy that depend on water include livestock, human settlements, aquatic systems, mining, and wildlife. A second component will analyze the effect on the supply and demand for land. The various sectors that depend on land include livestock and wildlife and to a lesser extent mining and human settlements. The Project will also support capacity building of government officials and stakeholders at national and local levels.
Ineffective mitigation of nonclimate drivers of ecosystem alteration | Impact: Moderately high (4) ; Probability: Low (1) | The government and UNDP has been working closely with the complementary Projects supported by GEF and bilateral donors, in order to ensure that non-climatic drivers of ecosystem alterations are sufficiently addressed. The Project will also ensure that outputs such as strategic environmental assessment, landscape level ecosystem adaptation plan, and regulatory and financial management techniques will inform other ecosystem management initiatives, and/or act as incentives for reducing nonclimatic threats to ecosystems. Capacity building for ecosystem based adaptation practices at community level will directly contribute to addressing nonclimatic drivers such as grazing pressure, hydropower, mining and agricultural planning. To date, the project supported to develop 3 regulations of Law on water pollution fee. Within regulations' framework, fees will be collected accordingly for water use, water pollution at standard level and fine for water pollution exceeding standards and special uses of state forest areas and incentive mechanism to be forced for replantation and clearing of forest by communities. Easy to understand training curricula and guidebooks on EbA local measures at international and national level and principles and practices of IWRM developed for further training of locals and decision makers.
Extreme natural disasters affect confidence of local community to adaptation measures | Impact: Moderate (3); Probability: Moderately low (2) | As a part of adaptation measures, the project will apply a proven approach of community-based disaster risk management, thus reducing the vulnerability of communities to natural disasters. The primary units will be the herder groups or community organizations joining the efforts. Local level demonstrations will provide incentives for the local communities to cooperate towards a long-term resilience. To date, a survey is being conducted on areas affected by forest and steppe fire that was identified as one of the priority issues during the local stakeholders discussions.
Capacity of Aimag and Soum level stakeholders will match project activity demands | Impact: Moderate (3); Probability: Moderately low (2) | Local level capacity building programme was developed to be realized throughout the project lifetime. This will be supported by a project capacity building strategy, including national/local mentoring programme.
Adaptation measures increase inequity | Impact: Moderate (3); Probability: Moderately low (2) | Survey is being done on gender ratio in connection to livelihood and poverty in 17 soums of the 3 aimags within framework of baseline studies. Additional data will be collected by Soum coordinators to be considered for further planning of EbA measures and small scale projects. The project will ensure that the adaptation measures are gender and other population group sensitive and demonstration at the local level that they do not limit the participation of women and the disabled as beneficiaries.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
No critical risks identified.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
N/A
Note on D9: Doungjun Roongruang: Level of risks?

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
|  | Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager / Coordinator: |  | Project Objective is to maintain the water provisioning services supplied by mountain and steppe ecosystems by internalizing climate change risks within land and water resource management regimes.
|  | Inception Phase of the Project completed |  | Inception Phase activities commenced in April, 2012. Within this phase, recruitment of the Project staff at both at Ulaanbaatar and local levels, the Inception workshop and Local stakeholder consultations were held. |  | Inception Phase activities commenced in April 2012 with establishment of the Project office and recruitment of team. As the implementing agency of the Project, the Ministry for Nature, Environment and Tourism (former MEGD) made a room available for the Project office. The Project was successfully organized the Inception Workshop on June 15, 2012 in the capital city, Ulaanbaatar, Mongolia. More than 90 participants representing the Government, relevant NGOs, and key stakeholders of the Project target areas were attended. In addition to the workshop, Local stakeholder consultations were held in both target landscapes between May 20 and June 3, 2012. The objective was to introduce the project design and underlying concepts of Ecosystem based Adaptation and provide background information on the status of water resources, ecosystem vulnerability to climate change impacts as well as the Adaptation Fund in the context of global climate finance mechanisms. | S
Outcome 1: Landscape level integrated land use and water resources monitoring and planning system focused upon reduction of ecosystem vulnerability to climate change.
|  | Strategic environmental assessment, including climate change considerations, conducted for target landscapes to document threats to ecosystem function and resilience and provide recommendations for avoiding and mitigating impacts. |  | 1. Baseline inventory/assessment (ecological and socio-economic) as a basis for the development of Ecosystem-based Adaptation Strategies for the target landscapes and River Basin Management Plans were completed. Apart from that, in cooperation with the National Agency of Meteorology and Environmental Monitoring (NAMEM), the Project has gathered all the required data as a basis of long term of environmental monitoring at target regions. 2. Vulnerability and Risk Assessment as a basis for developing EBA Strategies for the target landscapes and estimate the catchment surface and groundwater use balance in target River basins for developing RBMP are progressed. |  | 1. Baseline studies were conducted during the period from September 2012 to April 2013. The report on baseline studies includes collection, analysis of all related information and data and compilation reflecting the current situation on: (i) ecological condition including information on surface and ground water quantity and quality, wildlife, grassland, soil, forest, climate and geography; (ii) socio-economic condition including institutional capacity, policy and legislation framework. A data base with more than 170 indicators of the ecological and socio-economic sectors in targeted sites of the Project were being evaluated. From this a number of potential indicators were identified. The results of these studies will feed into development EbA landscape Strategy and RBMP. 2.The Project initiated Vulnerability and Risk assessments as a basis for development of EbA Strategy and RBMP as well as clarification of national capacity needs, which are keys to successful implementation of adaptation techniques in target areas. The assessment will be done compliant with the national environmental legislation and standards and use of environmental impact assessment methodologies, statistical analysis tools such as checklist, matrix analysis, and dynamic models (HBV, Century DAYCENT, NICHE, DSSAT, Maxcent ) and GIS system tools. The assessment will cover major components such as ecological vulnerabilities and risks, socio-economic vulnerabilities, the water use balance calculation and Climate change risk assessment (CCRA) of ecological and socio-economic sectors. Water use balance will be estimated with Vulneravility and Risk assessment with inclusion of surface and groundwater resources of the basin using existing outputs of baseline studies. | S
|  | Economic valuations completed summarizing landscape level costs and benefits of EBA. |  | Project's initial economic valuations initiated comparing the landscape level costs and benefits of EBA approaches. The purpose of the study is to assist in identification of the economically efficient adaptation strategies to climate change taking into full account the value of ecosystem services and biodiversity and will be a flatform to prioritize EBA local level strategies. |  | Since the evaluation requires cohesive approach and expertise using existing and newly simulated climate prediction and ecological models, the national experts are involved in on-the-job training, learning by doing and wide discussions. International expert shared and trained national experts and relevant stakeholders on cost and benefit principles, practices, data collection, processing and interpretation of results. Climate simulation has completely finished over targeted river basins from 1981 to 2011 using NCEP reanalysis data as initial and boundary data. The integrated model run interactively on the Super computer or installed on a PC and run using a RCM outputs. Ecological models (MAXENT, CENTURY and HBV) then wil use the climate simulated data on soil, forest, water and wildlife analysis (distribution, size/quantity and quality with regard of human settlements and influences etc.). | S
|  | Ecosystem-based Adaptation integrated within land use and water resources monitoring and decision-making system in two eco-regions. |  | The Project provided the NAMEM with technical support with aim to expand the monitoring network. |  | 1. Within the framework, the Project initiated procurement of required equipments such as Automatic Weather Station, ice drill, portable water lab, current meter with synthetic propeller, water-level sensor in order to improve the quality and accuracy of monitoing works for glaciers run-off, and surface and ground water measurements. 2. Constructing 12 m2 sized energy efficient dwelling for Glacier Base Camp in Kharkhiraa mountain is in progress. In cooperation with the GEF funded "Building Energy Efficient" Project implemented by UNDP, suitable design and technology for construction was identified. The site to construct dwelling is expected to be defined by HAMEM researchers in June, 2013. | S
Outcome 2: Landscape level adaptation techniques maintaining ecosystem integrity and water security under conditions of climate change.
|  | Local level climate change adaptation assessment and monitoring implemented in two target watersheds. |  | Soum level capacity assessment was carried out by a professional team. |  | With this assessment, local capacity with regard to EBA and IWRM activities was identified by categorized target groups such as soum and aimag level officers, herders, and NGO-s. Based on this, needs of trainings were identified. The assessment indicates that the knowledge and skills of local community is limited to undertake local level measures of EBA in a sustainable manner. In addition, the assessment pointed out that existing terms of references for soum level officials did not clearly state the duties and responsibilities concerning effective application of EBA concepts and participatory approaches for their works. Therefore, in cooperation with Aimag governments, the Project will develop Soum level EbA plans which will allow to revise and update of the existing terms of references for officials in charge of agriculture, environment and land management in order to reflect the above. | S
|  | Integrated landscape level Ecosystem-based Adaptation management action plans operational within two target watersheds. |  | 1. As preperation phase, based on Soum level capacity assessment, "Local level capacity building program" was developed to be realized throughout the Project lifetime. 2. Soum level project coordinators were trained on principles and practices of EBA and IWRM 3. A national consultant for conducting training on community based natural resource management and community-led impact monitoring techniques is selected on a competivie basis. |  | 1. In accordance with the workplan, the Project intends to prepare local level trainers (resource persons) specialized in EbA and IWRM planning. Environmental Units (ranger, officer in charge of land use, environmental inspector, meteorologist, veterinarian etc.) and the Project Soum Coordinators will be trained as trainers, who are expected to take a lead in the implementation of landscape level adaptation techniques at Soum level. 2. For building technical capacity of Soum level project coordinators, a training event was held in March, 2013 at the PIU in Ulaanbaatar. The main objective of the training was to build skills and knowledge of all soum coordinators in EbA strategy and IWRM principles and practices, and develop detailed workplan for year of 2013 on main activities of the Project. As a result of the training, trainees gained advanced level knowledge and skills on EBA and IWRM approaches and applications that have internationally and nationally been recognized and became familiar with participatory approaches as vital tools and techniques to motivate and mobilize local community for better collaborative actions and enhanced natural resource management. In addition, the participants were able to update their knowlegde and advanced skills on EBA and IWRM concepts and techniques. The trainees have been provided with all the necessary hand-outs and printed materials and will serve as trainers in their localities when necessary. 3. According to a ToR, the recruited consultant is expected to start duties starting from June, 2013 with objective of preparing local level trainers in Community Management Natural Management and Community-led Impact Monitoring. Main benefitiares will be environmental units, middle school teachers, environmental NGOs and Soum coordinators who in return train locals, students , farmers and herders. | S
|  | Suite of physical techniques to improve ecosystem resilience established in two target watersheds. |  | Feasibility study of physical techniques to improve ecosystem resilience to climate change will be conducted in 2013. Based on the study, required actions will be undertaken step by step. |  | TOR on feasibility study was drafted for recruitment process. The study will start in August, 2013. | S
|  | Regulatory and financial management techniques for improving climate change resilience implemented within two target watersheds. |  | As a preparation work, specific trainings on best practices on EbA at international and national levels, IWRM and sustainability of Community-based Natural Resources Management will be organized in 2013. After implementing these capacity building activities, actual EbA measures will be initiated in 2014 through implementing Small Grants Programme in target soums. |  | Training on funding mechanisms of small projects for establishment of EbA groups and mobilization of existing cooperatives/ nuhurluls (Forest User Groups, Pasture User Groups, Herder Groups) will be held in July, 2013 with combination of training on Community-based Natural Resource Management and CLIM. Associated legal environment on establishment of cooperatives/nuhurluls, its sustainability, rights and responsibilities of members and monitoring will be introduced to the targeted trainers. | S
Outcome 3: Institutional and policy capacity strengthened to support Ecosystembased Adaption replication, monitoring, and enforcement for critical watersheds
|  | Ecosystem-based adaptation approaches mainstreamed in national resource use planning and implementation mechanisms. |  | Assessment of Institutional Capacity for mainstreaming EBA approaches into development policy and planning of key agencies was completed. With the project support, capacities of several institutions including Ministry of Environment and Green Development, National Committee on Climate Change, Climate Change Coordination Office and Agency of Meteorology and Hydrology were assessed. Based on the assessment, specific recommendations were developed for ensuring better Instiututional capacity to mainstream EBA approaches into state policy and coordination. Furthermore, Capacity building programme was developed. |  | An assessment was conducted on technical and human capacities of relevant state institutions with strong engagement in climate change issues. In additon, relevant laws and national programs (The Laws on Environmental Protection, Forest, Fauna, Water, Air, Environmental Impact Assessment) were reviewed for further refinements in order to incorporate EBA concepts. Based on provided recommendations, the Project is cooperating with the MEGD to refine several significant regulations including water and forest use fee to ensure improving mentality for natural resource users. Finally, a draft Capacity building program was developed and submitted to the Minister of Environment and Green development for further consideration. | S
|  | Institutional support for integrating climate change risks in land and water resource management planning. |  | Public Awareness Programme disseminating EBA knowledge and information to general public was developed. Within the Programme, handbooks on EbA and IWRM were developed by professionals. As a complimentary part of the handbooks, training modules/ curriculums reflecting specific topics and delivering approaches were included to be used for different knowledge level users and trainers. These user friendly handbooks and associated training modules will be used as reference materials for further trainings. |  | Ways and methods to foster general public education with regard to EBA were identified and recommended. This will be used as a basic document to be considered and followed up to deal with public awareness raising issues within the Project objective. The program includes specific topics and activities designed for different knowlegde-level users. Implementation mechanisms and form of engagement of responsible parties to be considered were defined in detail and recommended. This is a basis for futher public awareness activities of the Project. As follow up activities of Public Awareness Programme, the products are designed as set of training packages including handbooks and training modules. The handbooks include general concepts and principles of EBA and IWRM and clear exapmles of national and international best practices, and pilot activities. Those activities can be underaken in the Project target soums. | S
|  |  |  | According to the Assessment of Institutional Capacity of key agencies, it is stated that it is necessary to improve relevant regulations of some Laws in order to mainstream EbA approaches into development policy and planning. Regarding this demand, totally 6 regulations of relevant Laws was newly developed and/or reformulated. |  | Set of Environmental Laws were revised and newly developed and approved by the Parliament of Mongolia in 2012. The project supported the development of following regulations in order to enhance the enforcement of newly approved Laws. Overall aim of these regulations is to promote economic entities that apply environmental sound technology and efficient use of water through provision of incentives. The regulations are expected to be a useful means to build proper mindset for sustainable us of natural resources. For implementation of Law on Water Pollution Fee: following 3 Regulations were reformulated and/or newly introduced: 1. Regulation on Household waste water tariff (consumers) 2. Regulation on setting water pollution charge 3. Regulation on Discount and excemption of water use charge and economic entity and organizations to be benefited from discount or excemption, and Setting of discount percentage: For implementation of Law on Forest: following 3 Regulations were reformulated and/or newly introduced: 1. Proposal for Regulation of procedure for the payment to owner for forest protection, restoration and nursery in case of timbering woods according to the permission of state authorized organization. 2. Proposal for Regulation on commercial activities undertaken in special purpose forest area of the State. 3. Proposal for common regulation of incentives | S
|  | Program for up-scaling best practices developed and implemented. |  | Development of Climate change website for distributing climate change and EbA related information with the aim to improve public awareness on climate change and EbA. |  | The Climate change coordination office (CCCO) had the webpage that was out-of-date, difficult to access and hard to modify. Therefore, a fully functional and easy to access web page was crucial to design which now became important tool and platform to share and disseminate information, knowledge and experience sharing, as well as to publicize CCCO and the Project activities and achievements to the public. The Climate change coordination office (CCCO) website is now accessible beginning on December 25, 2012 | S
| Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500) |  |  |  |  | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
|  | Name: | Tuya Tserenbataa, National Project Coordinator
|  | Email: | tuya.tserenbataa@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The Project has initiated to establish ecological and socio-economic benchmarks and baseline data as inputs for further planning and policy development documents such as River Basin Management Plans (RBMP) and EbA strategies. Programs and Action Plans for institutional and human capacity development, and public awareness and advocacy will be used further as significant guidance to implement a series of trainings with relevant topic and targeted stakeholders during the Project cycle. For the reporting period, training guidelines on RBMP, EbA principles and practices at local level were developed to increase knowledge and experience of stakeholders and used for training of trainers in target areas. In accordance with set of Environmental Laws newly amended and approved in 2012, the relevant 3 regulations of Law on water pollution fee and 3 regulations of Law on Forest were developed with the technical support of the Project. Overall aim of these regulations is to promote economic entities that apply environmental sound technology and efficient use of water, protection of trees and restoration of forest through provision of incentives. The regulations are expected to be a useful means to build proper mindset for sustainable use of natural resources. There is no negative progress so far observed.
|  | Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency |  | Outcome 1: Landscape level integrated land use and water resources monitoring and planning system focused upon reduction of ecosystem vulnerability to climate change. |  | Inception phase including initiation of establishment benchmarks as a basis for the development of Ecosystem-based Adaptation Strategies for the target landscapes and River Basin Management Plans are completed through contracting of experts teams to carry out assessments with wide discussions and carry out learning by doing and experience sharing trainings. Apart from that, preparation of establishment of additional surface water monitoring posts in 3 sites of the river basins and 1 glacial observation post in Western area was initiated in cooperation with the National Agency of Meteorology and Environmental Monitoring (NAMEM) for the purpose expansion of existing environmental monitoring network. Economic valuation of the targeted landscapes in two water sheds was progressed. |  | 1. The baseline study on ecology and socio-economic conditions of the two River basins was completed, final report submitted in March/April 2013 that allowed to revise and update the Project indicators in the Logical framework as well. 2. Economic valuation is underway and it requires cohesive approach to complete. The national consultants are progressing and benefiting with learning by doing, class room and on-job training and discussions and sharing experiences. Basing on completed climate simulation the cost and benefit analysis of the water, soil, pasture, forest and wildlife will be completed in 2013 by use of ecological models. 3. Expansion of environmental monitoring network was supported by initiation of procurement of equipments; authomatic weather station, portable laboratories for water quality, small house and measuring tools/equipments. NAMEM included in its plan to establish a new station at Uvs Lake in 2013, which will delegate personnel for the water and glacial observation posts in western target area. | S
|  | Outcome 2: Landscape level adaptation techniques maintaining ecosystem integrity and water security under conditions of climate change. Baseline and benchmarks for the development of the River Basin Management Plans at two River Basins and EbA Strategies at target ecoregions completed. |  | Two RBMPs and two EbA strategies will be developed and implemented |  | Preparatory works for development and implementation of the RBMPs and EbA strategies are aligned with planning of MEGD to establish and operate River Basin Administrations (RBA) at Ulz river and Turgen/Kharkhiraa rivers with consultations. As a result of it and Capacity development needs plan, series of trainings on IWRM, EbA strategy, hydrology, ecology and environmental policy for the staff of newly established RBAs and technical assistance on water and environmental monitoring are planned in 2013. Compilation of ecological and socio-economic conditions and series of discussions with relevant parties resulted progress report that was used in update of the Project Indicators as well. | S
|  | Outcome 3: Institutional and policy capacity strengthened to support Ecosystembased Adaption replication, monitoring, and enforcement for critical watersheds Institutional and policy improvements |  | Capacity of target and relevant stakeholders strengthened to develop and implement EbA strategies and River Basin Management Plans at two target areas. |  | A number of public awareness materials on EBA and River Basin Management principles and practices and climate change adaptation produced and disseminated, as a booklets/handouts and through CCCO website. A total of 6 regulations that support enforcement of 2012 amended/approved Laws on Fees on Water pollution and Law on Forest and were developed with the technical support of the Project. | S
|  | Inception phase completed |  | Local needs assessment and adaptive management conducted. Recruitment of Project staff and set up of office completed. The Inception workshop held with participation of relevant stakeholders. |  | The Project was succefully launched with participation of relevant stakeholders to introduce the Project goals and objectives and its implementation mechanisms; oversight, monitoring and Logical framework with indicators. The Project staff were fully recruited at Ulaanbaatar and local levels. 3 aimag coordinators were appointed and 9 Soum coordinators and 9 Soum drivers were recruited. Administrative Offices of Aimag and Soum Governments cooperate on implementation of the Project and provided work space for the Soum Coordinators. The Project Board and Techical Committee were established and the First Project Board Meeting was held to introduce Project Board (PB) roles and responsibilities and the progress of the Project and to get PB comments on 2013 Annual work plan. Technical Committee was called to meet three times to review and comment on progress of baseline studies and economic evaluation. | S
[6 empty] | Overall Rating | S+
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
|  | Name: | Chimeg Junai, Programme Analyst
|  | Email: | chimeg.junai@undp.org
|  | Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other |  | See above.
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
|  | Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | In overall, the Project achievements were satisfactory in terms of products and outcomes planned in the reporting period. It was important to set up the Project office with full staff both at central and local level to ensure smooth run of the implementation. Priority actions were to collect and compile baseline data on ecology and socio-economic conditions of the target areas. Other preparatory work such as human and technical capacity building, and public awareness programs were completed. Training guidelines were developed for stakeholders who will play a main role in development of the RBMP and EbA strategies. Moreover, advocacy of the Project was done with active involvement of relevant bodies of MEGD. These were structural and organizational changes of the Ministries and agencies after Parliamentary election that resulted in some delays, including establishment of the Project Board, organisation of meetings and technical workshops.
Rating Definitions
[5 empty] | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major objectives/outcomes for given reporting period, without major shortcomings. The project can be presented as “good practice”.
[5 empty] | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major objectives/outcomes with only minor shortcomings.
[5 empty] | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant objectives/outcomes, but with either significant shortcomings or modest overall relevance.
[5 empty] | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major objectives/outcomes with major shortcomings or is expected to achieve only some of its major objectives/outcomes.
[5 empty] | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major objectives/outcomes.
[5 empty] | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its objectives/outcomes.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator |  | Baseline | [7 empty] | Progress since inception | Target for Project End
Project overall Indicator | Mean annual in-stream summer 30-day base flow maintained (not decreased) in two project sites (Kharkhiraa/Turgen, Ulz) |  | Kharkhiraa River: | 2.43 m3/sec | [6 empty] | Baseline studies determined mean average annual in-stream summer 30-day in Kharkhiraa/ Turgen and Ulz River basin for 2012. Kharkhiraa River: 3.17 m3/sec, Turgen River: 2.32 m3/sec, Ulz River: 0.0 m3/sec | Kharkhiraa River: 2.43 m3/sec
|  |  | Turgen River: | 1.98 m3/sec | [7 empty] | Turgen River: 1.98 m3/sec
|  |  | Ulz River: (the current monitoring station (Chuluunkhoroot) for the Ulz river is located at a channel without water.) | 0.0 m3/sec | [7 empty] | Ulz River: 0.10 m3/sec (at Chuluunkhoroot)
| Surface water quality improved or maintained in two project sites (Kharkhiraa/Turgen, Ulz) |  | Water chemical analysis (long term average) | Tur-gen River |  | Khar-khiraa River |  | Ulz River |  |  | *Please note that the baseline data here and in the logframe is the average of data gathered through long term monitoring (10 and more years). Surface water quality and composition in Kharkhiraa/ Turgen and Ulz Rivers are identified through Baseline studies in 2012. However, these data from one year is not appropriate to compara with the baseline data. Thus, data will be annually collected at similar sites throughout the Project lifeteme, and the emerging average is expected to be compared with the baseline. | 5% improvement on average
|  |  | Suspended solids (mg/l) | 70* |  | 2 |  | 43.2
|  |  | Permanganate COD (mg/l) | 0.3 |  | 0.5 |  | 6.8
|  |  | NH+4 (mg/l) | 0.28 |  | 0.07 |  | 0.31
|  |  | Total mineral P (g/l) | 0.36 |  | 0.014 |  | 0.21
|  |  | Total Fe (mg/l) | 0.049 |  | 0.13 |  | 0.064
|  |  | Soil nutrient, organic carbon (matter) pool | Turgen/ Kharkhiraa Rivers basin |  |  |  | Ulz River basin |  |  | The same as above.
|  |  |  | Type of soil name |  | Depth, cm | Humus % | Type of soil name | Depth, cm | Humus %
|  |  |  | Dry steppe pale-brown soil |  | 0-20 | 0.8 | Dark kastanozem soil | 0-20 | 5.6
|  |  |  | Swampy soil brown soil |  | 0-20 | 22.1 | Light kastanozem soil | 0-20 | 3.2
|  |  |  | Saline soil |  | 0-20 | 5.8
|  |  | Biological indicators, e.g., insect and/or fish | Turgen/ Kharkhiraa Rivers basin |  |  |  | Ulz River basin |  |  | Biological indicators will be defined by local monitoring groups from target sites to be established in 2013. Survey on mammals will be conducted jointly with related research institutions prior to the midterm evaluation and final year of the Project implementation.
|  |  |  | Type of indicators | Indicators name | Year | Population number | Indicators name | Year | Population number
|  |  |  | Mammals | Argali sheep (Ovis ammon) | 2009 | 1033 | Procapra gutturosa | 2002 | 800000- 900000 ps
|  |  |  | Fishes | Phoxinusczekanowskii | 2012 | + | Phoxinusczekanowskii | 2012 | ++
[5 empty] | Ph. lagowskii | 2012 | + | Ph. lagowskii | 2012 | ++
[5 empty] | Ph.percnurus | 2012 | + | Ph.percnurus | 2012 | +
|  |  |  | Insects | (Ephemeroptera)- Ameletus inopinatus Eaton, 1887 | 2012 | ++ | (Ephemeroptera)- Baetidae-Baetis sp. | 2012 | ++
[5 empty] | (Plecoptera)- Isoperla sp. | 2012 | ++ | (Plecoptera)- Perlidae-Agnetina sp. | 2012 | ++
|  |  |  | Birds | Altai snowcock | 2012 | + | Grus vipio Pal | 2012 | +
|  |  | Remarks | Status: +-rare; ++ normal; +++- abundant
|  |  | Surface water temperature (Celsius) | Turgen River ( in September 2012) |  | Kharkhiraa River ( in September 2012) |  | Ulz River ( in September 2012) |  |  | Surface water temperature will be measured jointly with Provincial Meteorological offices of target aimags each year in summer time.
|  |  |  | 13 (Celsius) |  | 12 (Celsius) |  | 20.5 (Celsius)
Indicator of outcomes | 1.1 Number of integrated strategies/ management plans for river basins approved and adopted by National and Aimag Governments |  | Operational integrated strategies/management plans for river basins(or sub-basins) | [5 empty] | 0 |  | Preparation of the integrated strategies/ management plans has started in 2013. Baseline studies will feed into management planning. Integrated strategies/management plans will be made for Kharkhiraa/ Tugren and Ulz Rivers basin; further progress will be reported in the next PPR. | at least 2
| 1.2 Number of Aimag governments monitoring, assessing, and reporting to MEGD and relevant agencies (water authority, National Climate Change Coordination Office) on integrated river basin management measures |  | Number Aimag Governments implementing integrated strategies/management plans for river basins: | [5 empty] | 0 |  | The implementation of these plans will begin in January 2014. | at least 3
| 1.3 Total hectares included within protected areas system in the two project sites (Kharkhira/Turgen, Ulz) |  | Altai Mountains / GLB: | [5 empty] | 37,420 km² |  | No changes during the reporting period. | Altai Mountains / GLB: 39,420 km²
|  |  | Kharkhiraa/Turgen Watershed: | [5 empty] | 800 km² |  |  | Kharkhiraa/Turgen: 1,000 km²
|  |  | Eastern Steppe: | [5 empty] | 42,676 km² |  | No changes during the reporting period. | Eastern Steppe: 44,676 km²
|  |  | Ulz Watershed: | [5 empty] | 3,120 km² |  |  | Ulz: 3,750 km2
| 2.1 Number of Soums in target area considering EBA measures/Integrated River Basin Management into their annual land-use planning and in Soum development plans and strategies. |  | Total number of Soums in target area considering integrated River Basin Management in their annual land-use planning and in Soum development plans and strategies: | [5 empty] | 0 |  | The project is planning to achieve this goal step by step. Strong capacity of relevant parties are expected to be a platform of dealing with this issue. For the reporting period soum level capacity assessment was carried out by a professional team. With this assessment, local capacity was identified by target groups such as soum and aimag level officers, herders, and NGO-s. Considering this assessment results, the project is planning to organize systematic and detailed trainings wihs specific reference to EBA and IRBM for project soums. As a preparatory work of above mentioned trainings, hand outs and training programms on EBA and IRBM were prepared by professors of National University of Mongolia and University of Humanities. These handbooks and training programs will be used as reference materials for further trainings. | 17
| 2.2 Water use efficiency improved to maintain ecosystem integrity as measured by: | 2.2.1 Amount of surface water extracted for irrigation in project sites (cubic meter) | Kharkhiraa/Turgen River basin: | [5 empty] | 4,829,600 m3 |  | The baseline data was determined by baseline survey conducted in 2012 in the Kharkhiraa/ Turgen Rivers basin. Next survey will be conducted jointly with related research institutions prior to the midterm and final evaluation of the Project implementation. | Kharkhiraa/ Turgen Rivers basin: approx. 10% of average annual flow
|  |  | Ulz River basin: | [5 empty] | 0 |  | No irrigation system in Ulz River basin. | 0
|  | 2.2.2 Number of monitored wells increasing ground-water consumption efficiency in project sites | Kharkhiraa/Turgen River basin: | [5 empty] | 0 |  | Number of monitored wells in target river basins will be identified by Feasibility study to be conducted in 2013. Relevant field level activities will be commenced in 2014. | 12
|  |  | Ulz River basin: | [5 empty] | 0 |  |  | 70
|  | 2.2.3 Small scale Rain and snow melt Water harvesting | No water harvesting activities | [5 empty] | 0 |  | Number of small scale and snow melt water harvesting in target river basins will be identified by the Feasibility study . Relevant field level activities are expected to be commenced in 2014. | Number of small scale water harvesting reservoirs
| 2.3 Land use practices and climate change resilience improved as indicated by: | 2.3.1 Total hectares of riparian and wetland habitat restored with native vegetation within project sites | Kharkhiraa/Turgen River basin: | [5 empty] | 0 |  | The project plans to conduct feasiblity study to define sites and priority actions of EBA in target soums in 2013. Based on findings of this assessment, areas and sites to be rehabiliated will be identified. Relevant field level activities are expected to be commenced in 2014. | Approx. 30% increase
|  |  | Ulz River basin: | [5 empty] | 0
|  | 2.3.2 Springs protected with livestock exclosures, Livestock watering and access to creeks managed with appropriate facilities/fencing | Kharkhiraa/Turgen River basin: | [5 empty] | 0
|  |  | Ulz River basin: | [5 empty] | 0
|  | 2.3.3 Total area with improved pasture land management | Target sites | [5 empty] | -
|  | 2.3.4 Areas with Reforestation and improved forest management in Western target areas | 226 ha | [7 empty] | The baseline data was determined by the baseline survey conducted in Western target soums from 2010 to 2012. This area includes forest areas with reforestation, reafforestation and, area of cleaning and thining. | Western target areas: 226 ha (approx. 10% increase)
| 2.4 Decrease in average Rural Poverty rate for 17 Soums within the target watersheds. |  | Current poverty rate: Kharkhiraa/Turgen basin: | [5 empty] | 0.495 |  | Rural Poverty rate for the target basins can be determinied by end of 2013 applying the UNDP census-based poverty map of 2012 and data from National Statistical Office of Monoglia for 2012. | Approx. 10% average decrease
|  |  | Average Poverty headcount for Ulz basin: | [5 empty] | 0.433
| 2.5 Number of Small Enterprises established and operating successfully |  | Kharkhiraa/Turgen River basin: | [5 empty] | 312* |  | Baseline data were determined by the baseline studies conducted in 2012. | 570 Small Enterprises at both project sites (appr. 5% increase).
|  |  | Ulz River basin: | [5 empty] | 237*
| 2.6 Hydrological monitoring is strengthened |  | Monitoring posts for glacial run-off in Western project area: | [5 empty] | 0 |  | Establishing monitoring post for glacial run-off in western target area is in progress. So far, the site have been identified by relevant instiutuion. In addition, expanding of water resources monitoring network is initiated in Eastern target soums. | At least 1 in Western target area; at least 2 in Eastern target area
| 3.1 Number of River Basin Administrations (RBA) established and strengthened in target two watersheds |  | Operational RBAs: | [5 empty] | 0 |  | The action to establish RBAs in target two watershed was initiated. Supportive actions for the establishment of RBAs such as training and technical capacity building were planned in Annual Work Plan (AWP) for 2013. | 2
| 3.2 Number of River Basin Councils (RBC) established and strengthened in target two watersheds |  | None of operational RBCs in target two watersheds | [7 empty] | Not started yet | 3
| 3.3 Number of staffs of relevant agencies and local governments trained in river basin management guidelines |  | 0 | [7 empty] | The guideline on RBMP principles and concepts was developed for public and decision-makers. Project unit members both working at central and local office were trained for trainers on RBMP principles and concepts. RBMP for target two watersheds and relevant workshops and trainings were planned in AWP for 2013 | at least 21 experts including staffs of relevant agencies in each 21 aimags (provinces), and members of RBAs and RBCs.
| 3.4 Number of Soums replicating EBA measures and integrated river basin management principles and practices within the target eco-regions |  | 5 | [7 empty] | Public Awareness Programme of EBA principles and practices were developed and 20' documentary film to increase public knowledge and information on the state of ecosystem, its services and value was broadcasted. | at least 20
| 3.5 National mainstreaming of EBA as indicated by: | 3.5.1 Number of official government policy documents adopting EBA principles/practices | 6 | [7 empty] | Set of Environmental Laws were revised and newly developed and approved by the Parliament of Mongolia in 2012. The project supported the development of following 6 regulations in order to enhance the enforcement of newly approved Laws. Overall aim of these regulations is to promote economic entities that apply environmental sound technology and efficient use of water through provision of incentives. The regulations are expected to be a useful means to build proper mindset for sustainable us of natural resources. For implementation of Law on Water Pollution Fee: following 3 Regulations were reformulated and/or newly introduced: 1. Regulation on Household waste water tariff (consumers) 2. Regulation on setting water pollution charge 3. Regulation on Discount and excemption of water use charge and economic entity and organizations to be benefited from discount or excemption, and Setting of discount percentage: For implementation of Law on Forest: following 3 Regulations were reformulated and/or newly introduced: 1. Proposal for Regulation of procedure for the payment to owner for forest protection, restoration and nursery in case of timbering woods according to the permission of state authorized organization. 2. Proposal for Regulation on commercial activities undertaken in special purpose forest area of the State. 3. Proposal for common regulation of incentives | at least 7
|  | 3.5.2 Amount of annual government spending to support application of EBA principles and practices nationally | Total national annual investment in EBA: | [5 empty] | 0 |  | Not started yet | 100000
|  | 3.5.3 Number of National Climate Change Authority EBA policy documents mainstreaming EBA within sectoral decision-making frameworks. | Number of National Climate Change Authority Policy Documents: | [5 empty] | 0 |  | Assessment of Comprehensive Institutional Capacity Building for internalizing EbA approaches into development policy and planning of key agencies (MEGD*, National Committee on Climate Change, Climate Change Coordination Office and Agency of Meteorology and Hydrology etc) was conducted. | at least 3

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please Complete the following section every reporting period |  | 4/5 | -
Implementation and Adaptive Management | Response
Describe any implementation issues/lessons affecting progress (positive and negative)
Were there any delays in implementation? If so, include any causes of delays. What are the measures taken to reduce delays? | Were there any delays in implementation? If so, include any causes of delays: There is 2-month delay in conducting baseline study and soum level assessment, due to the central and local parliament election held in June and November 2012 respectively. After the election, it took some time to set up new government cabinet. Through re-structuring of the government, the appointment of several heads of departments and divisions of the Ministry of Environment and Green Development, that have a strong cooperation with the project took some time, impacting the delay of project activities. In addition, there was also a delay in recruitment of Project core staffs in the first half of the year due to the limited number of experts with high qualification and skills required for the posts. Also the newly recruited project staff had to take time for induction and practices in the Project assignments and tasks following the Government and UNDP rules and regulations. What are the measures taken to reduce delays?: The UNDP CO took action providing a support staff with significant experiences on effective delivery of outcomes and products. In addition after the recruitment of two new experts in October, 2012, the project worked hard in 3th and 4th Quarter in order to complete delayed activities. Also the Project established technical commitee comprising of nationally recognized scientists and highly qualified experts from Mongolian Academy of Sciences and leading universities. Recommendations and contributions of the newly established commitee were valuable to reduce the delays.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | During the reporting period, set of environmental laws were amended and approved by the Parliament of Mongolia. New concepts such as establishment of River Basin Administration (RBA) and RBA Management Plans were introduced into the Law on Water and Law on Water pollution fee. In this regard, supportive actions and cooperation to facilitate newly established RBAs in two project target regions are integrated into the logical framework through rephrasing, applying the newly introduced terms as RBA, RBA Management Plan.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Gender consideration was taken into account in the baseline studies. No lesson has been generated on this to date as the project is in its early stage.
Please Complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilent Measures
Please Describe the Climate Resilent measures being undertaken by the project/programme.
Which of these masures has been most effective and why?
Which have been least effective and why?
Concrete Adaptaiton Interventions
Please desribe the concrete adaptation measures being undertaken by the project/programme
What are/were the most difficult aspects of implementing such measures?
What are/were the most successful aspects of the implementation of the interventions?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
Describe what kind and how existing information/data/knowledge has been used to inform the development and the implementation of the project.
If Learning Objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what why have they contributed?
What have been the major lessons learned that would add to the knowledge base for dissemination within and beyond the project area?

## AF Tracking Tool
Tracking Tool for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Please select the relevant Fund level Outcome and Output indicators that allign with the project objectives and outcomes
OBJECTIVE 1: Integrated Strategies/Management Plans for target landscapes/river basins developed and under implementation.
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) |  | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 3 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 3.1 | With the project support, EbA strategy and RBMPs for targeted basins will have been developed and implemented with engagement of local authority and community. Approximately, 90 percent of targeted populaton will be aware of predicted adverse impacts of climate change and of appropriate responses. More than 20 percent of the targeted population will have been trained and involved in community-led environmental impact monitoring and Communtiy based Adaptation. |  | Awareness and ownership of EbA and climate risk reduction processes at local level are insufficient. No actions are taken to dissiminate information on adverse impacts of climate change and appropriate responses. Local level authorities have limited experience and skills to develop and implement special programs and strategies with the aim of providing local community with required ecological education on EbA.
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) |  | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 3 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 3.1 | Basic surveys and ( Baseline study, vulnerability and risk assessment and Economic valuation) have been initiated in the target sites. Findings of these studies will be used as a platform for EbA strategy and RBMPs. Participatory approaches will be widely used for development of the strategy. 90 percent of the population will be provided with information on the strategy. |  | Awareness and ownership of EbA and climate risk reduction processes at local level are insufficient. No actions are taken to dissiminate information on adverse impacts of climate change and appropriate responses. Local level authorities have limited experience and skills to develop and implement special programs and strategies with the aim of providing local community with required ecological education on EbA.
OBJECTIVE 2: Implementing landscape level adaptation techniques to maintain ecosystem integrity and water security under conditions of climate change.
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement |  | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 5 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 5 | By the end of the Project, approximately 12000 persons will have been trained and involved in Ecosystem based Adaptation (EbA) measures at 17 target soums. Local level officers will have required knowledge and skills to serve as local level trainers to disseminate specific EBA techniques suited to socio-ecological condition of their locality. |  | Knowledge and skills of project stakeholders including local authority , and local community is completely limited with regard to increasing ecosystmem resilience in response to climate change and variability -induced stress
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement |  | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 5 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 5 | During the project implementation, trained communities will be provided with opportunity to apply their obtained knowledge and skills for climate change adaptation activities. At least, 5 demonstration activies with specific reference to increasing ecosystem resillience in responce to climate change will be undertaken in each soum. |  | Knowledge and skills of project stakeholders including local authority , and local community is completely limited with regard to increasing ecosystmem resilience in response to climate change and variability -induced stress.
OBJECTIVE 3: Strengthening capacities/Institutions to support EbA strategies and integrated river basin management, their replication and mainstreaming in sector policies.
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement |  | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 7 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 7 | By the end of the project, EbA are intergrated and mainstreamed into National Policy and regulations. More specifically, EbA approaches will be nationally recognized and applied for any decisions related to environment and climate change issues. |  | National and local level policies and regulations to promote EbA measures are extremely weak. National Action Plan on Climate Change is approved by The Government of Mongolia. However, it does not explicitly reflect EBA approaches that suited to Mongolian economic and ecological conditions.
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement |  | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 7 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 7.1 |  | By the end of the project, totally 2 River Basin Administrations (RBAs) and 2 River Basin Councils (RBCs) are established and strengthened in two target watersheds. | Currently, RBAs and RBCs in two target project watersheds are not established and operational yet . In accordance with newly approved Law on Water, these structures are expected to be establised in 2013. Therefore, there is an urgent need for project technical assisstance to the RBAs and RBCs to be established.
[5 empty] | By the end of the project, staffs of relevant agencies and local governments in target regions will be trained and obtained necessary knowledge and skills through a series of systematic trainings organized by the project. As a result, sustainability of new RBAs and RBCs are ensured beyond the project termination. | Currently, RBAs and RBCs in two target project watersheds are not established and operational yet . In accordance with newly approved Law on Water, these structures are expected to be establised in 2013. Therefore, there is an urgent need for project technical assisstance to the RBAs and RBCs to be established.
[5 empty] | By the end of the project, more than 10 relevant regulations with regard to water and forest recourses will be amended and approved which reflect EbA concept and principles. | The Set of Environmental Laws were amended and approved by the Parliament of Mongolia in 2012. In relation to this, there is a need for refinement on relevant regulations in order to ensure favorable legal environment for EbA.

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.