## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | July 2012-June 2013
| Project Title: | Enhancing Adaptive Capacity of Communities to Climate Change-related Floods in the North Coast and Islands Region of PNG
| Project Summary: | The impact of climate change-related hazards in the Papua New Guinea (PNG) country has been increasing in intensity and frequency. Further impacts from climate change include the loss of food gardens due to extensive flooding (both in coastal and riverine areas) combined with extended periods of drought. The rising sea level is causing some of PNG’s islands to be gradually submerged. Salt water intrusion is affecting groundwater particularly in the islands and in coastal areas, threatening domestic water supplies and agriculture. With the onset and multitude of climate change impacts, the country’s economy, environment and people are becoming more vulnerable and are at risk of not meeting basic human development needs. Climate change puts at risk the achievement of the goals set out in PNG’s major development plans. Flooding in the coastal areas is one of the most important climate change related hazards in the North Coast and the Islands Region as settlements are usually located in the coasts, particularly the provincial capitals of East Sepik (Wewak), Madang (Madang), Morobe (Lae), and West New Britain (Kimbe). Similarly, in the hinterland areas, climate change-related inland flooding is the most pressing hazard with the largest potential for wide-spread damage. The overall objective of this programme is to enhance the adaptive capacity of communities to make informed decisions about and adapt to climate change-driven hazards affecting both coastal and riverine communities in the North Coast and Islands Region of Papua New Guinea. In particular, the programme will focus on resilience towards occurrences of coastal and inland flooding events. The proposed programme will contribute to several outcomes and outputs listed within the Adaptation Fund Strategic Results Framework.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | PIMS 4452 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilaterial | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Papua New Guinea | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | East Sepik, Madang, Morobe, New Ireland and Northern Provinces in Papua New Guiena | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2012-03-23
IE-AFB Agreement Signature Date: |  | 2012-03-26 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2012-07-26 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned):
Terminal Evaluation Date:
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | National Inception Workshop Report, New Ireland Provincial Stakeholder Consultative Meeting, | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Jacob Ekinye (from Executing Agency - OCCD - acting project manager on part-time basis); Maureen Ewai (starting October 2013) | Dominican Republic
| Email: | jacobekinye@gmail.com | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: | Varigini Badira | Equatoral Guinea
| Email: | vbadira@gmail.com | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | David McLachlan-Karr | Fiji
| Email: | david.mclachlan-karr@one.un.org | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Jacob Ekinye | Georgia
| Email: | jacobekinye@gmail.com | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | Emmajil Ahai-Bogari | Grenada
| Email: | emmajil.rowanna@gmail.com | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Manau Renagi | Guyana
| Email: | manaurenagi@gmail.com | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 30 June 2013
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 30 June 2013 | 88365
Add any comments on AF Grant Funds. (word limit=200) | Two factors contributed to the rather low delivery: (a) the national general election processes between April - August 2012 and the subsequent adjustments/re-alignments in the government bureaucracy which has taken time; (b) diffiulty in attracting the best candidates for the PMU positions on account of the stiff competition posed by demand from the rapidly expanding resource extractive sector. Nevertheless, a qualified project manager has now been hired and will be on board in October 2013. In the interim, the government (OCCD) with support from UNDP PNG led the implementation of the project and carried out some activities. It is expected that project implementation will be accelerated with the PM on board. The National Disaster Center and National Weather Services and the pilot provinces are keen to expedite delivery. UNDP, as part of its oversight functions will look into the reported concern during the inception workshop and steering committee meetings about the escalation of costs in PNG due to the rapidly expanding economy fueled by the extractive resource sector. The PNG currency has been appreciating as a result. Government adn UNDP will ensure that the impacts of these developments will be minimal through continuously looking at cost-efficient approaches; decisions will be reflected in future reports.
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Components 1 and 2 - Climate Change related Coastal Flooding; : New Ireland Provincial Stakeholder Consultative Workshop; agreeements reached with provincial government on succeeding activities at the provincial level; TOR for Hazards Assessment Completed and Disseminated for Tender (Activities 1.1.1 and 2.1.1) Output1.2 Coastal flood preparedness and response plan and systems established in the North Coast and Islands Region | 9962.96
| Component 3 - Institutional Strengthening to support climate and disaster resilient policy frameworks: Project Steering Committee Meeting with participation from all provinces. Provinces will initiate the compilation of policies relevant to the project for comprehensive review by consultant. 3.2 Policy makers and planners at the national, provincial and district offices, institutions and extension services | 26443.9
| Project Execution - National Project Inception Workshop and Recruitment of PMU Staff | 51958.16
| TOTAL | 88365.02
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| ACTIVITY 1: Adaptation to Coastal Flooding-related Risks and Hazards for North Coast and Islands Region Communities | 1503537 | 2014-07-01
| 1.1 Coastal early warning systems established for observation, data collection and information management and dissemination in the North Coast and Islands Region | 277155
| 1.2 Coastal flood preparedness and response plan and systems established in the North Coast and Islands Region | 340000
| 1.3. Support system for community-led mangrove reforestation and conservation projects | 200000 |  | 455000
| 1.4 Integrated coastal adaptation measures implemented to protect 8 communities in East Sepik Province, Oro Province and New Ireland Province. | 686381.91
| ACTIVITY 2: Adaptation to Inland Flooding-related Risks and Hazards for Riverine Communities in East Sepik, Northern, Madang and Morobe Provinces | 1216500 | 2014-07-01
| 2.1 Inland flooding early warning systems established for observation, data collection and information management and dissemination in the provinces of the North Coast and Islands Region | 245692.97
| 2.2 Inland flood preparedness and response plan and systems established in the North Coast provinces | 300000
| 2.3 Integrated riverbank protection measures implemented to protect 8 communities in East Sepik Province, Oro Province and Morobe and Madang Provinces | 670807.03
| ACTIVITY 3: Institutional Strengthening to Support Climate and Disaster Resilient Policy Frameworks | 348556 | 2014-07-01
| 3.1 Climate change-related risks and resilience from coastal and inland flooding integrated into coastal zone management related polices, legal and planning frameworks at the national and sub-national levels | 141286.54
| 3.2 Policy makers and planners at the national, provincial and district offices, institutions and extension services systemically trained to implement climate-sensitive policies and plans | 207269.46
| ACTIVITY 4: Awareness Raising and Knowledge Management | 116000 | 2014-07-01
4.1 Lessons learned and best practices generated, captured and distributed to other communities, civil society, policy makers in government and globally through appropriate mechanisms
| 4.2 Climate change awareness and education programmes carried out to build next generations' resilience to climate change | 116000
| Activity 5: Project Management and Coordination | 229130 | 2014-07-01
| TOTAL | 3413723
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Procurement
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  | None
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signiture Date | Payment to Date | Remaining Balance
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
Name of Contract , Procruement Method, Date of Call
Name of Contract , Procruement Method, if appicable Date of Call
Name of Contract , Procruement Method, if appicable Date of Call
Name of Contract , Procruement Method, if appicable Date of Call
Name of Contract , Procruement Method, if appicable Date of Call

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Insufficient collaboration between project implementation partners and stakeholders | M | Representation at the Project Steering Communittee is inclusive of all relevant stakeholders, Regular updates of the project at the monthly climate change technical working group meetings have been conducted.
Weak cooperation by communities at proposed sites | M | Not applicable during the reporting period; project has not initiated/planned work at the community level.
Land use disputes within the communities affect implementation of project activities and plans | L | Not applicable during the reporting period; project has not initiated/planned work at the community level.
Limited human resources in PNG’s national and provincial agencies to adequately support to the activities and ensure the sustainability of the adaptation measures | M | A Climate Change Capacity Assessment is now being planned to prioritise training needs at the national, provincial, district and local level governments including private sector and civil society organisations. Ongoing training and awareness initiatives attended by a wide range of stakeholders
A series of unusually adverse climatic conditions impacts the adaptation measures being implemented, or weakens the interest of key stakeholders to address adaptation issues. | L | Not applicable during the reporting period; no adverse climatic conditions occurred.
The best practices and adaptation measures adopted are not gender sensitive – i.e. they increase inequity between men and women or change the social roles of men and women in a way that reduces self reliance. | M | Not applicable during the reporting period; this will be tackled when the project moves to plan and implement concrete adaptation measures.
The selection of pilot sites does not follow the established criteria and is derailed due to political processes and influences. | L | Close consultattions with provincial governments were undertaken during the Inception Workshop, Steering Committee Meeting and provincial consultation to ensure objectivity in the selection process. The planned hazard assessment will provide objective basis for site selection.
The government is not supportive, politically and financially, to a cross-sectoral and integrated approach to the management of climate risks and opportunities. | L | Not applicable during the reference period: however, the planned support for the review and finalisation of the Climate Change Policy to providing the overall framework as requested by key stakeholders in public and private sectors.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The project is facing stiff competition from the fluorishing resource extractive industry in attracting the best candidates for the full-time project positions (National Program Coordinator - NPC, Admin and Finance Specialist and Technical Specialist). Qualified professionals are in short supply relative to demand from all sectors. | M | The part-time National Program Director assigned by the implementing partner (OCCD) has agreed to take the lead in implementing the project with support from UNDP PNG while the search is ongoing. The involvement of OCCD and UNDP PNG staff is on a part-time basis. The lengthy search is expected to be completed with a suitable candidate identified and could soon be taking on the the post of National Project Coordinator. The candidate is motivated by strong professional interest in CC-A and the environment.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Refer to critical risk affecting progress (not identified at project design). The impact of the described steps to mitigate risk with respect to accelerating progress has been limited; a fulltime project manager (PM) is critical to move the project forward. Nevertheless, the interim leadership of the NPD from OCCD was able to keep the momentum gained during the project inception workshop held in July/Aug 2012. Earlier in 2013, a suitable candidate has been offered the PM post and is going through the final recruitment process and expected to report in October 2013. Once the NPC is on board, progress will be accelerated to make up for the delays.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Establishment of Project Office Space and Recruitment of Project Management Unit staff following the national Inception Workshop |  | National inception workshop and steering committee meetings conducted; Project Management Unit staff fully mobilized |  | National inception workshop completed; project steering committee meetings completed; one provincial consultation completed | Unsatisfactory
| No progress on all activities under all outcomes areas |  | Completion of all initial activities as per the Gantt Chart/Multiyear WorkPlan for the first year were delayed |  | TORs prepared for Hazard Assessment, Provincial Consultation ongoing | Unsatisfactory
[5 empty] | Overall Rating | Unsatisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Gwen Maru
| Email: | gwen.maru@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The absence of project management unit staff slowed down the progress in the implementation of planned activities as per the Annual Work Plan. Remedial measures included the involvement of the National Project Director assigned by OCCD and UNDP PNG in continuing the momentum of the project after the inception workshop. However, progress has been limited as these staff had other responsibilities. OCCD with the support of UNDP PNG has accelerated the hiring of the National Project Manager and the selected candidate is expected to take on the post in October 2013. The Project Administrative and Financial Assistant is expected to started in September 2013.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Significant delay for the recruitment of staff for the Project Management Unit |  | To have project management unit staff on board for the national inception workshop |  | National inception workshop and two steering committee meetings completed without the staff | Unsatisfactory
| Significant delay in implementing planned Annual Work Plans in the first year |  | Initial engagement with key partners for implementation, Establishment of coordination mechanisms at the provincial level, Increased interest generated at the provincial levels to participate in the pilot project |  | Insignificant progress on most aspects except for work on preparing for Hazard Assessment, Capacity Assessment and Capacity Building Workshops planned for third quarter | Unsatisfactory
[5 empty] | Overall Rating | Unsatisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Jacob Ekinye
| Email: | jacobekinye@gmail.com
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | There was no mid-term review as the project only started in July 2012 with the national inception workshop. However, despite the slow start in the first year, the project management unit staffs are expected to be on board in the third quarter 2013. In addition, the provinces have expressed interest and demonstrated commitment to be directly involved in implementation of activities hence it is likely that PNG will make good progress towards achieving the project outcomes. The actions to address the unsatisfactory ratings are: i) Conduct Capacity Assessment to identify capacity needs and develop a training plan on both technical and operational aspects of project to expedite implementation; ii) Continous engagement with key partners to guide and ensure timely inputs to coordinate and facilitate implementation; iii) Strengthen capacity of OCCD with a technical specialist on climate change adaptation; iv) Improve awareness and advocacy on the project at the national level.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective - Strengthened ability of coastal and riverine communities in Papua New Guinea to make informed decisions about and to undertake concrete actions to adapt to climate change-driven hazards affecting their specific locations | 1. Number of risk-exposed coastal communities protected through adaptation measures | In the current scenario, risk-exposed communities are to a large extent unable to adapt to climate change due to a lack of resources, capacity, knowledge and the necessary support through provincial and national institutions as well as policy frameworks. With the scale of adaptation measures planned for implementation the total population in the 16 targeted communities would be an estimated 32,000 | Nil | By the end of the project at least 8 coastal communities are protected through adaptation measures against coastal flooding scenarios, with attention to the special concerns of women as participants and beneficiaries.
| 2. Number of risk-exposed riverine communities protected through adaptation measures |  | Nil | Eight (8) riverine communities are protected through adaptation measures against inland flooding, with attention to the special concerns of women as participants and beneficiaries
| 3. Number of provinces with improved climate-related planning and policy frameworks to increase resilience |  | Nil | At the end of the programme, adaptation to climate change is managed, monitored and planned at the provincial level in the targeted provinces and supported by a framework of policies and plans including disaster preparedeness and response plans, coastal zone management plans.
Outcome 1 - Reduced exposure and increased adaptive capacity of coastal communities to flood-related risks and hazards in 8 communities and three cities of the 11 provinces of the North Coast and Islands Region. | 1. Number of communities benefitting from improved protection from coastal floods | The vast majority of communities exposed to coastal flooding is inadequately equipped with resources, capacity and support to adapt to the heightened risks from climate change The total number of inhabitants in the 8 target coastal communities that are vulnerable to coastal flooding is estimated at 16,000. An additional population of 120,000 in the cities of Lae, Wewak and Madang will benefit from the programme’s implementation | Nil | By the end of the project, 8 communities are protected from coastal flooding through adaptation measures that were put in place in a community-led way with the agreements/compacts agreed on by communities to preserve the mangrove forests
| 2. Number of AWS and voluntary weather stations in operation 3. Number of communities covered by the improved coastal warning system and weather information | There is lack of equipment and capacity of the PNGNWS, hence, the forecasting of disasters and extreme weather events is severely limited. |  | At least 6 tidal gauges and at least 6 AWS and 10 voluntary weather stations established at strategic locations, meet WMO standards and contribute to the monitoring and early warning system. One AWS will have been installed in each target 8 communities.
| 4. Number of provinces wth comprehensive disaster prepared ness and response plans for coastal flooding in place | The provincial and national-level disaster management frameworks are evidently inadequate to address the risks | Ongoing | At least four provinces will have a comprehensive disaster preparedness and response plans for coastal flooding in place and will have conducted dry run tests.
| 5. Number of provincial capitals with assessed engineering measures for adaptation | No effort has been done on this aspect in the target provincial capitals. | Nil | For three provincial capitals of Lae, Madang and Wewak suitable coastal engineering measures for adaptation are identified and addressed through respective planning and funding.
| Number of community-led mangrove projects benefitting from support system for mangrove projects | Community-based mangrove projects are undertaken ad-hoc and largely without sufficient expertise and support | Nil | 33 community-led mangrove conservation and/or reforestation projects, covering about 100 hectares are supported through the support network and nurseries
| Number of mangrove nurseries established and sustainably operating | None | Nil | Eight (8) regional nurseries operate sustainably supplying the requirements of the target sites and replication areas
| Resources allocated for continued operations of the nurseries |  | Nil | Before the end of the project, sufficient resources are allocated by government for the continued operations of the nurseries beyond the life of the project.
Outcome 2 - Reduced exposure and increased adaptive capacity of 8 riverine communities in 4 provinces | Number of communities benefitting from improved protection from inland flooding | The vast majority of communities exposed to inland flooding risk is inadequately equipped with resources, capacity and support to adapt to the changed scenario The total number of inhabitants in the 8 target riverine communities that are vulnerable to coastal flooding is estimated at a minimum 32000 people. | Nil | By the end of the project, eight communities are protected from inland flooding through adaptation measures that were put in place in a community-led way.
| Number of communities covered by the improved warning system and weather information Number of AWS and voluntary weather stations in operation | Disaster preparedness is limited by the lack of and state of facilites and plans There is lack of equipment and capacity of the PNGNWS is weak, hence theh forecasting of disasters and weather patterns is limited. | Nil | At least 6 AWS and at least 20 voluntary weather stations established at strategic locations, meet WMO standards and contribute to the monitoring and early warning system. One AWS will have been installed in each target 8 communities.
| Number of provinces with comprehensive disaster preparedness and response plan for inland flooding | The provincial and national-level disaster managment frameworks are evidently inadquate | Nil | At least four provinces will have a comprehensive disaster preparedness and response plan for inland flooding in place and will have conducted dry run tests.
Outcome 3 - Strengthened institutional capacity at national and sub-national levels to integrate climate change-related risks into sectoral policies and management practices | Number of national and provincial level policies, strategies, plans and coordinating mechanisms reviewed and incorporating resilience to climate change | Adaptation to the changed climate scenario of the present and future is inadequately considered in national and provincial level policies and planning frameworks | 1 Provincial Coordination Committee launched | At the end of the project, all major development plans in the targeted provinces reflect climate change and adaptation considerations and coastal zone management policies are developed for the most populated areas (especially Wewak, Kavieng, Madang, Lae)
| Number of provincial and national-level officers trained in climate adaptation planning and implementation | At the provincial level the lack of resources, capacity and in some cases basic management mechanisms/plans is evident | Nil | At the provincial level, there is a strong link between all climate change officers/focal points and the communities in their respective provinces and the officers are equipped with the resources and capacity to identify and manage adaptation needs in the province
| Participation of women in project activities | Participation of women is very minimal | Nil | Increased (at least 20%) number of women participating in capacity building activities at national and subnational level
Outcome 4 - Strengthened awareness and ownership of adaptation and climate change-related risk reduction processes at national and sub-national levels | % of the risk-affected population exposed to awareness raising activities and materials | Awareness raising efforts is ad-hoc, uncoordinated and often undertaken with insufficient technical basis | Nil | 75 % of the risk-affected population is exposed to awareness raising activities and materials.
| Integration of climate change into the national school curricula and university academic programmes | Only few schools cover climate change in their classes and activites; there is very limited guidance for teachers | Nil | The topics of climate change and adaptation are introduced in PNG’s school curricula and university academic programmes and teachers are equipped with the required knowledge and material
| Amount of funding mobilized via CSR and sponsorship agreements | CSR funding sources is currently nil. | Nil | By the end of the project agreements on continuation of awareness raising and adaptation activities (especially replication) through contributions from Corporate Social Responsibilty programmes and private sector participation are reached (including projects under infrastructure tax credit schemes) and make resources available for the community-led adaption in at least 10 further communities (estimated 500,000 USD)

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Delays in recruitment of PMU staff and interim arrangement whereby OCCD took over project implementation was inadequate due to limited capacity in OCCD itself.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Delay in recruitment of Project Management Unit staff as well as limited capacity in OCCD itself as indicated above.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | Some provinces expressed interest to implement the project hence capacity assessment in scheduled for third quarter for 2013. In addition, PMU will be staffed in the coming months which will accelerate implementation.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Yes, both men and women recognised that their joint efforts are required to lead and coordinate implementation of adaptation measures where necessary. With the delays, there is still limited scope for taking gender considerations into account.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | No climate adaptation measures implemented to date
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | No climate adaptation measures implemented to date
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | No concrete adaptation interventions implemented to date
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | No concrete adaptation interventions implemented to date
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Not applicable at this time
What measures are/have been put in place to ensure sustainability of the project/program results? | Not applicable at this time
What measures are being/could have been put in place to improve project/program results? | Not applicable at this time
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Not applicable at this time
If learning objectives have been established, have they been met? Please describe. | Not applicable at this time
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Lack of agency cooperation to provide important hazard data for the 5 provinces
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Not applicable at this time

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Please select the relevant Fund level Outcome and Output indicators that align with the project objectives and outcomes
OBJECTIVE 1
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 1 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 1 | Adequate threat and hazard information on coastal and inland flooding disseminated in 8 coastal and 8 riverine communities reducing climate related risks to the affected population | A preliminary EWS has been set up recently with private public partnership established to disseminate information using mobile services. However, coastal and inland communities are still inadequately prepared to respond to flooding risks due to lack of knowledge, resources and capacity
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 5 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 5 | Critical coastal ecosystems restored to protect coastlines and provide livelihoods | Critical coastal ecosystems are degraded due to lack of recognition of the protective functions of coastal ecosystems
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 1 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individual or community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced+D16 | 1.2 | Early warning systems in 8 coastal and 8 inland communities installed | Forecasting and of disasters and extreme weather events is severely limited at the community levels due to lack of equipment and capacity of the PNGNWS
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 5 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individual or community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced+D16 | 5 | 33 community-led mangrove conservation and/or reforestation projects are supported | No community-led mangrove conservation and/or reforestation projects ongoing in targeted communities
OBJECTIVE 2
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 2 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 2.1 | At the end of the project, major development plans in the targeted provinces reflect climate change and adaptation considerations | At the national level, a Climate-Compatible Development Strategy (CCDS) and Interim Action Plan has been developed. However, there at the provincial level, there are no development plans or policies that adequately consider adaptation to the changed climate scenario
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 2.1 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individual or community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 2.1.2 | At the provincial level, there is a strong link between all CC officers/focal points and the communities and staff capacity to identify and manage adaptation needs increased | There is lack of resources and capacity to understand and respond to climate change, due to the lack of CC officers/focal points at the provincial level
OBJECTIVE 3
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 7 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 7 | Critical coastal ecosystems restored to protect coastlines and provide livelihoods | The protective functions of coastal ecosystems are not generally recognized
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 7 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individual or community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 7.1 | Climate change risks and resilience to flooding integrated into national and provincial planning frameworks | National economic and land-use planning frameworks have not yet sufficiently integrated climate change risks and flood resilience. The Environmental Impact Assessment process does not take climate change into consideration
OBJECTIVE 4
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 3 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 3.1 | Communities in the coastal and inland areas targeted by the intervention are aware of adaptation and climate risk reduction processes | Communities in the coastal and inland areas targeted by the intervention are not sufficiently aware of adaptation and climate risk reduction processes due to lack of effective knowledge products and education programmed
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 3 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individual or community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 3.1 | 50% of the community members in the coastal and inland areas targeted by the intervention are exposed to awareness raising activities and materials | Community members in the coastal and inland areas targeted by the intervention are not exposed to sufficient awareness raising activities or materials

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.

## Compatibility Report
Compatibility Report for Copy of PNG AF Project Progress Report_July12-July13.xls
Run on 9/18/2013 21:30
The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when opening this workbook in an earlier version of Excel or if you save this workbook in an earlier file format.
Significant loss of functionality | # of occurrences | Version
One or more cells in this workbook contain data validation rules which refer to values on other worksheets. These data validation rules will not be saved. | 3
| FinancialData'!E54 | Excel 97-2003
| Procurement'!E49:H49 | Excel 97-2003
| Risk Assesment'!E57 | Excel 97-2003
Minor loss of fidelity
Some formulas in this workbook are linked to other workbooks that are closed. When these formulas are recalculated in earlier versions of Excel without opening the linked workbooks, characters beyond the 255-character limit cannot be returned. | 2 Defined Names | Excel 97-2003
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 183 | Excel 97-2003