## Slide 1: Adaptation Fund Webinar on Decisions of the 42nd AFB meeting Gap analysis for project implementation policies revision
Martina Dorigo
Climate Change Specialist
Portfolio Management

## Slide 2: background
The AFB approved two policies to support adaptive management practices:
Policy for Project/Programme Implementation (OPG Annex 7) October 2017 - Decision B.30/39
Policy for Project/Programme Delays (developed in 2013 and last updated in October 2019) - Decision B.34-35/12
Since then, the portfolio has been growing and expanded to different type of projects (e.g., EDA, innovation, and upcoming funding modalities under MTS II).
Notes: With a view of supporting adaptive management practices of the funded projects and programmes, the Adaptation Fund Board (the Board) approved two policies containing provisions to guide Implementing Entities (IEs) in the processes to be followed in case of need of project post approval changes.

## Slide 3: BACKGROUND
Policy for Project/Programme Implementation
Revisions to the project results framework
Direct project services
Policy for Project/Programme Delays
Delays in project inception (regular projects and readiness grants)
Material change (budget variation at output level involving 10% or more of the total budget)
No-cost extension of project completion date
Notes: Direct project/programme services are services provided by the implementing entity to an executing entity by undertaking some of its execution duties on its behalf. Such services could be identified prior to project approval or during implementation, as the executing entities that are to provide those services can estimate that they are unable to do so. Such services may relate for instance to procurement and payment management.
Justification for the RDPS explaining how the costs were established, along with a letter from the Designated Authority of the Adaptation Fund for the country(ies) of the project/programme endorsing the RDPS.
_______________________________
Project inception delays:
To approve options 2 and 4, as described in document AFB/EFC.27/3, for addressing project and programme inception delays;
To grant a maximum extension of 12 months for the inception of projects and programmes, subject to their compliance with the requirements under option 2;
To require any implementing entity whose project or programme experiences, due to exceptional circumstances, a significant delay in inception (exceeding 12 months from the standard inception target of six months from the first cash transfer) to submit to the Board, through the Adaptation Fund Board Secretariat, a “Request for revision of the project implementation schedule, including a revised inception date” for intersessional consideration;
To request the secretariat to communicate to implementing entities the monitoring requirement(s) under option 2. Update on resource mobilization strategy and action plan 70. (Decision B.36/35)
The approval of the ‘Request for extension of Project Inception’ by the secretariat would follow the standard review process of such request by the secretariat and reviewed against the following criteria:
The request for extension of inception delays should be reasonable and sufficiently justified considering the context, rationale and with a proposed plan for improvement of the overall project implementation;
Any request for extension of inception delay which might lead to project restructuring, disbursement schedule changes and other major changes in the project design and implementation will be considered ineligible for this option, and therefore IEs will be advised to submit a request in accordance with OPG Annex 7;
AFB/EFC.27/3 The extension cannot exceed a maximum period of 12 months and IEs will be required to submit a revised project implementation plan taking into account the 12-month delay;
In line of the policy on project and programme delays, the request for extension of project start date must be submitted by the IE at least 2 months prior to the initial project start date as indicated in the approved proposal document.
No-cost extension: An implementing entity may request for a project/programme extension beyond the original completion date for up to 18 months for a concrete adaptation project/programme if (i) no additional funds are required; (ii) the project/programme’s originally approved scope will not change; and (iii) the entity provides reasons and justifications for the extension. The DA must be notified of an extension request. Additional time beyond the 18 months stated above may be granted under exceptional circumstances.
Additionally in Dec. 2020, to continue delivery projects and programmes and mitigate impacts on the performance of projects/programmes funded by the Fund, the Board has approved at the second session of its thirty fifth meeting (Board Decision B.35.b/16), a set of measures as immediate actions to mitigate the effects of the pandemic on its portfolio. A blanket no-cost extension of project completion date up to 12 months for the concrete adaptation project/programme which has been delayed due to COVID-19 and was set to be completed within next 24 months. The ad interim measures are still into effect, secr. Will present a separate analysis on the trend of requests for discussion at the next EFC meeting, to consider whether to terminate these measure.
Board in March 2023 approved, through Decision B.40/69, updated measures available to Implementing Entities (IEs) as follows:
  Set a limit of two requests per project for a no-cost extension of a project completion date delayed due to COVID-19 as referred to in the Decision;
The blanket no-cost extension will be in effect during the period of the COVID-19 pandemic and until terminated by the Board.
Please note that the list in annex 1 does not include the COVID-19 related extension requests which were temporarily allowed by paragraph (b) of decision B.35.b/16 provided that such requests met the criteria described in paragraph 33 of document AFB/EFC.26.b/4, given that the secretariat has provided an update to the EFC at its thirty-first meeting (AFB/EFC.31/.9) and that the Board subsequently provided further guidance on this specific cases of extension requests through Decision B.40/69. 46 requests received so far (of these three during this past inters. Period).

## Slide 4: DECISION B.42/49
Observations on post-approval requests for changes received by the Adaptation Fund Board Secretariat
Having considered the recommendation of the Ethics and Finance Committee, the Adaptation Fund Board decided to request the secretariat:
To prepare a gap analysis of the current policies pertaining to project post-approval requests for changes, namely the policy on project/programme implementation (annex 7 to the Operational Policies and Guidelines) and the policy on project/programme delays (AFB/B.34-35/6);
To develop options for addressing the gaps identified, including, as necessary, suggestions for amendments to the policies;
To present the results of (a) and (b) above to the Ethics and Finance Committee for its consideration at its thirty-fourth meeting.

## Slide 5: PROCESS TO ADDRESS BOARD DECISION
Objective:
GAP analysis of current project implementation policies:
      Identify areas which need more clarity
      Identify areas on which guidance is needed (current gaps)
      Take into account different projects types (readiness; EDA; etc.)
      How?
      Survey to be circulated to IEs to have inputs on above points
      Sister climate funds comparative analysis
      When?
      June (survey)
      June/July paper development